## Slide 1
ONBOARDING PROGRAM WALKTHROUGH
ABSA × EXL
Model Hosting Platform
A 6-month program to onboard 10 production models with end-to-end
governance, security and chain-of-custody from intake to scoring delivery.

## Slide 2
Why we're here
01 / Context
The opportunity
ABSA has 10 production-grade risk and decision models running today across multiple
environments. EXL will host the scoring runtime end-to-end — taking signed code
and data from ABSA, scoring it on a controlled platform, and returning auditable
outputs on the agreed cadence.
The platform we deliver must satisfy banking-grade audit, security and change-
management requirements while being repeatable enough to onboard new models
without re-architecting.
Auditable
Every artefact signed; every action logged; full chain-of-custody from intake to delivery.
Repeatable
Pipeline templates and a model registry turn new-model onboarding from weeks into days.
Cross-account
ABSA and EXL operate in separate AWS accounts with cryptographically verifiable hand-offs.
ABSA × EXL • Onboarding Program Walkthrough
2 / 13

## Slide 3
Delivery at a glance
02 / What we're committing to
10
models in scope
6
months to go-live
9
delivery phases
85+
tracked tasks
11
milestone gates
How the 10 models split
Group 1 (2 models, Month 4): proof of the chain end-to-end. ABSA sign-off here is the biggest single milestone.
Group 2 (8 models, Months 5-6): parallel ramp; reuses Group 1 templates so per-model cost falls sharply.
What success looks like at Month 6
10/10
models in scheduled production scoring on EXL-hosted infrastructure
100%
of scoring runs cryptographically signed + verifiable end-to-end by ABSA
Self-service
template-driven onboarding for any new model in the same family
ABSA × EXL • Onboarding Program Walkthrough
3 / 13

## Slide 4
Program timeline
03 / Six months at a glance
M1
M2
M3
M4
M5
M6
M7+
Governance & Scope
Architecture, Access & Connectivity
Data & Code Readiness
Platform Foundation Build
Controls & Change Mgmt
Code Optimization & Pipelines
Group 1 — First 2 models
Group 2 — Remaining 8 models
Dashboards & Delivery
Steady State Support
New Model Onboarding (template)
Critical milestone: Group 1 sign-off (end of Month 4) gates Group 2 and steady state. Schedule slippage here cascades.
ABSA × EXL • Onboarding Program Walkthrough
4 / 13

## Slide 5
Months 1-2: Set the foundation
04 / Phases 1-3
1
Governance & Scope
Month 1
Confirm SPOCs on both sides
Agree 10-model delivery sequence
Lock run cadence per model
Agree PIR + sign-off checkpoints
ABSA shares approved model docs + code + benchmarks
GATE TO NEXT PHASE
SPOCs identified, scope sign-off
2
Architecture & Connectivity
Months 1-2
ABSA architecture sign-off
EXL provisions AWS landing zones
Cross-account IAM trust established
Encrypted S3 replication path validated
SSO federation tested + signed off
GATE TO NEXT PHASE
Real account IDs + IAM principals exchanged
3
Data & Code Readiness
Months 1-2
ABSA freezes input variables
ABSA prepares signed code package
First code+data+benchmark transferred to EXL
EXL validates receipt via code-intake
EXL runs schema + drift quality checks
GATE TO NEXT PHASE
First model accepted by code-intake
ABSA × EXL • Onboarding Program Walkthrough
5 / 13

## Slide 6
Months 2-6: Platform & Controls
05 / Phases 4 & 5
Phase 4: Platform Foundation Build
Months 2-3 • EXL leads, ABSA consulted on key choices
Landing zone + networking
Multi-account topology per ADR-0004; baseline IAM/KMS
Model registry + version control
FastAPI registry + DynamoDB; approval state machine
Pipeline templates
Standard-batch / Scalable-batch / Realtime placeholder ready
CI/CD + drift gates
GitHub Actions workflows publishing signed manifests
Audit + observability
Append-only event log + LocalStack-based regression demo
Infrastructure-as-Code
Terraform modules for every component, per-env stacks
Phase 5: Controls & Change Management
Months 2-6 • Cross-cutting
Change-request workflow + approval matrix
Peer review + promotion gates for production
Rollback requirements per change
Data retention + archival rules
Secure access controls for delivery endpoints
Release logging in agreed tracking tool
ABSA × EXL • Onboarding Program Walkthrough
6 / 13

## Slide 7
Months 3-4: Optimize, then prove it
06 / Phases 6 & 7
Phase 6: Code Optimization & Pipeline Setup
Months 3-4 • EXL leads
Review developer code for production readiness
Standardize + optimize model scoring code
Validate scoring logic vs dev benchmarks
Package scoring code for controlled deployment
Create reusable scoring pipeline templates
Register models + pipeline versions in registry
Set up model run schedules
CRITICAL MILESTONE
Phase 7: Group 1 — First 2 models
Month 4 • Joint EXL + ABSA • Gates Group 2 + steady state
Why this is critical
Group 1 is the proof point. We prove the chain end-to-end on two real models — intake, sign, score, reconcile, PIR — before scaling to the remaining 8. ABSA sign-off here unlocks every downstream phase.
Exit criteria
Outputs reconcile to ABSA benchmarks
Defects resolved, PIR complete
ABSA Risk Owner sign-off in writing
ABSA × EXL • Onboarding Program Walkthrough
7 / 13

## Slide 8
Months 5-7+: Scale + steady state
07 / Phases 8 & 9
Group 2: Remaining 8 models
Months 5-6
Group 1 templates reused
Parallel onboarding stream
Per-model PIR + reconciliation
ABSA sign-off closes initial scope
Dashboards & Delivery
Months 5-6
Monitoring dashboard for runs + exceptions
Alert routing for failures
Secure output delivery to ABSA
Operational runbooks + handover material
Steady State Support
Month 7+
Scheduled daily/weekly/monthly scoring
Audit trail per run + delivery
Drift + anomaly review cadence
Quarterly service review with ABSA
New Model Onboarding
Month 7+
Template-driven for same model family
Type-specific controls for new categories
Validation + scoring + PIR per model
Register + schedule new approved models
ABSA × EXL • Onboarding Program Walkthrough
8 / 13

## Slide 9
Who owns what
08 / Ownership across the program
ABSA owns
Architecture sign-off + internal cloud approvals
Source datasets, input variables, signed code packages
Benchmark outputs for reconciliation
IP whitelisting + connectivity details
Group 1 & Group 2 sign-off (PIR closure)
Approving new model onboarding requests
EXL delivers
AWS landing zone, IAM, KMS, secrets
Model registry + pipeline templates
Code intake validation + manifest signing
Scoring runtime + audit trail
Monitoring dashboards + alerting
Operational runbooks + handover material
Both run jointly
Governance, scope, RACI, cadence
Cross-account IAM trust + SSO
Encrypted transfer validation
Change management + approval matrix
PIR + benchmark reconciliation
Quarterly service review
ABSA × EXL • Onboarding Program Walkthrough
9 / 13

## Slide 10
Key risks & mitigations
09 / Top 5 we're actively managing
Severity
Risk description
Mitigation
HIGH
ABSA account onboarding (real account IDs + IAM principal ARNs) delayed
Pre-stage Terraform; LocalStack-based regression demo keeps CI green; escalate by end Month 1
HIGH
Group 1 sign-off slips, cascading into Group 2 + steady state
Use Group 1 as dress rehearsal; pre-stage Group 2 templates so the ramp doesn't wait
HIGH
ML compute platform choice (SFN+Lambda vs SageMaker) blocks Phase 4
Decision required end of Month 2; surface to architecture review board this week
MEDIUM
Benchmark reconciliation discrepancies force scoring-code rewrite
Validate scoring logic incrementally during code optimization; record per-feature deltas
MEDIUM
Data quality issues (drift, schema mismatch) in initial intake
Run code-intake validate on first arrival; reject + return to ABSA the same day
ABSA × EXL • Onboarding Program Walkthrough
10 / 13

## Slide 11
What we've already built
10 / Platform ready today
We aren't starting from zero. The hosting platform is built end-to-end and runs the
full chain locally every PR — code intake to verifier — so day 1 of real onboarding
is configuration, not construction.
✓
Code Intake validator
5 checkers (Python static, SAS structural, schema, tests, PIR) with per-package venv isolation
✓
Pipeline Factory
Deterministic ASL renderer with 3 templates (standard-batch, scalable-batch, realtime placeholder)
✓
Manifest Signer
KMS asymmetric signing + verify-online / verify-offline / verify-from-bucket CLIs
✓
Registry API
FastAPI + DynamoDB with approval state machine and append-only audit log
✓
LocalStack End-to-End Demo
Full producer + verifier chain runs in CI on every PR; sample transcript committed
✓
Ops Runbooks
KMS key rotation, LocalStack demo, day-2 operating procedures
ABSA × EXL • Onboarding Program Walkthrough
11 / 13

## Slide 12
What we need from ABSA
11 / Unblocks real Phase 2-7
These seven items unblock the real Phase 2-7 work. Until they arrive, the LocalStack
demo keeps the platform regression-tested but we cannot move scoring to real AWS.
1
AWS Account IDs (ABSA receiving accounts + any additional EXL accounts)
2
IAM Principal ARNs requiring kms:Verify, kms:GetPublicKey, s3:GetObject access
3
SAS runtime (Docker image + license terms) for full SAS validation
4
PIR system contract (API spec or feed format for the mapping authority)
5
Data movement choice (S3 cross-account replication vs SFTP)
6
CAB / IVU API contract for governance integration
7
Network connectivity decision (VPC peering / Transit Gateway / PrivateLink)
ABSA × EXL • Onboarding Program Walkthrough
12 / 13

## Slide 13
NEXT STEPS
Where we go from here
01
This week
Confirm SPOCs and circulate the master task tracker. Schedule the kickoff with steering committee.
02
Next 2 weeks
Lock open decisions: ML compute platform, data-movement path, real-time tier SLA. Architecture sign-off.
03
Next 30 days
ABSA shares Group 1 model code + benchmarks. EXL stands up landing zones. First package validated via code-intake.
04
Next 90 days
Platform built. Code optimized. Group 1 onboarded and reconciled. ABSA sign-off targeted end of Month 4.
Questions? Reach the Program Office or your assigned SPOC.