## Master Task List
ABSA x EXL Model Hosting — Master Task List
Task ID | Phase | Category | Task | Owner | RACI: R | RACI: A | Priority | Effort (d) | Start | End | Duration (d) | Dependencies | Status | Delivery | Risk | Notes
T001 | P1 | Project Governance & Scope | Confirm project kickoff agenda and stakeholder list | BOTH | BOTH | Steering Committee | Critical | 2 | 2026-01-01 | 2026-01-04 |  |  | Not Started | Planned | Low | Kickoff meeting
T002 | P1 | Project Governance & Scope | SPOCs from ABSA and EXL | BOTH | BOTH | Exec Sponsor | Critical | 1 | 2026-01-04 | 2026-01-07 |  | T001 | Not Started | Planned | Low | Single Points of Contact each side
T003 | P1 | Project Governance & Scope | Finalize governance structure and working cadence | BOTH | BOTH | Steering Committee | Critical | 3 | 2026-01-07 | 2026-01-10 |  | T002 | Not Started | Planned | Low | Weekly standup + monthly steering
T004 | P1 | Project Governance & Scope | Review scope, exclusions, assumptions, dependencies | BOTH | BOTH | Steering Committee | High | 3 | 2026-01-10 | 2026-01-13 |  | T003 | Not Started | Planned | Medium | RACI + dependency log
T005 | P1 | Project Governance & Scope | Agree delivery plan for the initial 10 models | BOTH | BOTH | ABSA Risk Owner | Critical | 5 | 2026-01-13 | 2026-01-16 |  | T004 | Not Started | Planned | Medium | Sequencing: Group 1 (2) -> Group 2 (8)
T006 | P1 | Project Governance & Scope | Confirm run frequency for each of the initial models | BOTH | BOTH | ABSA Risk Owner | High | 3 | 2026-01-16 | 2026-01-19 |  | T005 | Not Started | Planned | Low | Daily / weekly / monthly cadence per model
T007 | P1 | Project Governance & Scope | Share approved model documents (initial set) | ABSA | ABSA | ABSA Model Owner | Critical | 5 | 2026-01-19 | 2026-01-22 |  | T002 | Not Started | Blocked | High | Model dev specs + validation reports
T008 | P1 | Project Governance & Scope | Share model code, supporting artefacts, benchmark outputs | ABSA | ABSA | ABSA Model Owner | Critical | 5 | 2026-01-22 | 2026-01-25 |  | T007 | Not Started | Blocked | High | Reference golden data for reconciliation
T009 | P1 | Project Governance & Scope | Agree PIR expectations and sign-off checkpoints | BOTH | BOTH | ABSA Risk Owner | Critical | 3 | 2026-01-25 | 2026-01-28 |  | T004 | Not Started | Planned | Medium | Post-Implementation Review framework
T010 | P1 | Project Governance & Scope | Create project logger | EXL | EXL | Program Mgr | Medium | 2 | 2026-01-28 | 2026-01-31 |  | T003 | Not Started | Planned | Low | Jira / Confluence / equivalent
T011 | P2 | Architecture, Access & Connectivity | Review target architecture + secure transfer approach | BOTH | BOTH | Architecture Board | Critical | 5 | 2026-01-15 | 2026-01-18 |  | T001 | In Progress | Partial | Medium | ADRs 0001-0010 capture decisions
T012 | P2 | Architecture, Access & Connectivity | Approve final architecture for implementation | ABSA | ABSA | ABSA Architect | Critical | 3 | 2026-01-18 | 2026-01-21 |  | T011 | Not Started | Blocked | High | Awaits ABSA sign-off
T013 | P2 | Architecture, Access & Connectivity | Complete ABSA internal cloud approvals | ABSA | ABSA | ABSA Architect | Critical | 10 | 2026-01-22 | 2026-01-25 |  | T012 | Not Started | Blocked | High | ABSA-side governance
T014 | P2 | Architecture, Access & Connectivity | Provision EXL AWS landing zone accounts + baseline access | EXL | EXL | EXL Cloud Eng | Critical | 5 | 2026-01-26 | 2026-01-29 |  | T013 | Not Started | Partial | Medium | terraform/account-bootstrap/ ready
T015 | P2 | Architecture, Access & Connectivity | Set up IAM trust for cross-account connectivity | BOTH | BOTH | ABSA Architect | Critical | 3 | 2026-01-29 | 2026-02-01 |  | T014 | Not Started | Partial | Medium | signing-foundation module wires policy
T016 | P2 | Architecture, Access & Connectivity | Complete IP whitelisting for approved endpoints | ABSA | ABSA | ABSA Network | High | 3 | 2026-02-02 | 2026-02-05 |  | T013 | Not Started | Blocked | Medium | ABSA-side firewall rules
T017 | P2 | Architecture, Access & Connectivity | Share secure tunnel and connectivity details | ABSA | ABSA | ABSA Network | High | 2 | 2026-02-06 | 2026-02-09 |  | T016 | Not Started | Blocked | Medium | VPC peering / TGW / PrivateLink decision
T018 | P2 | Architecture, Access & Connectivity | Configure encrypted S3 replication path | BOTH | BOTH | ABSA Architect | High | 5 | 2026-02-09 | 2026-02-12 |  | T015,T017 | Not Started | Partial | Medium | s3-replication-{source,destination} modules ready
T019 | P2 | Architecture, Access & Connectivity | Validate end-to-end encrypted transfer | BOTH | BOTH | ABSA Architect | High | 3 | 2026-02-13 | 2026-02-16 |  | T018 | Not Started | Planned | Medium | Real-account test
T020 | P2 | Architecture, Access & Connectivity | Finalize domain mapping for access endpoints | BOTH | BOTH | ABSA Network | Medium | 3 | 2026-02-17 | 2026-02-20 |  | T015 | Not Started | Planned | Low | DNS / Route 53 plan
T021 | P2 | Architecture, Access & Connectivity | Configure SSO federation | BOTH | BOTH | ABSA Identity | High | 5 | 2026-02-20 | 2026-02-23 |  | T015 | Not Started | Planned | Medium | Identity provider integration
T022 | P2 | Architecture, Access & Connectivity | Joint SSO testing + sign-off | BOTH | BOTH | ABSA Identity | High | 3 | 2026-02-24 | 2026-02-27 |  | T021 | Not Started | Planned | Medium | After Phase 2 dependencies clear
T023 | P3 | Data & Code Readiness | Confirm source datasets + file structure per model | ABSA | ABSA | ABSA Data Owner | Critical | 5 | 2026-01-15 | 2026-01-19 |  | T005 | Not Started | Blocked | High | Per-model data dictionary
T024 | P3 | Data & Code Readiness | Freeze input variables + requirements (initial set) | ABSA | ABSA | ABSA Risk Owner | Critical | 5 | 2026-01-19 | 2026-01-23 |  | T023 | Not Started | Blocked | High | PIR mapping authority
T025 | P3 | Data & Code Readiness | Provide access to original dev environment | ABSA | ABSA | ABSA Model Owner | High | 5 | 2026-01-24 | 2026-01-28 |  | T024 | Not Started | Blocked | Medium | For code optimization (Phase 6)
T026 | P3 | Data & Code Readiness | Prepare scoring-ready data at agreed cadence | EXL (ABSA Side) | EXL (ABSA Side) | ABSA Data Owner | High | 8 | 2026-01-29 | 2026-02-02 |  | T024 | Not Started | Blocked | Medium | EXL operates inside ABSA's data plane
T027 | P3 | Data & Code Readiness | Prepare signed code package with documentation | ABSA | ABSA | ABSA Model Owner | Critical | 8 | 2026-02-03 | 2026-02-07 |  | T008 | Not Started | Blocked | High | Package contract spec is in repo (ADR-0010)
T028 | P3 | Data & Code Readiness | Transfer scoring-ready data, code, benchmarks to EXL | ABSA | ABSA | ABSA Data Owner | Critical | 3 | 2026-02-08 | 2026-02-12 |  | T019,T026,T027 | Not Started | Blocked | Medium | Cross-account S3 replication path
T029 | P3 | Data & Code Readiness | Validate receipt, completeness, integrity [Vishnu's Repo] | EXL | EXL | Tech Lead | Critical | 2 | 2026-02-13 | 2026-02-17 |  | T028 | Done | Done | Low | code-intake validate runs 5 checkers
T030 | P3 | Data & Code Readiness | Run data-quality checks: schema, volume, drift [Vishnu's Repo] | EXL | EXL | Tech Lead | High | 3 | 2026-02-18 | 2026-02-22 |  | T029 | In Progress | Partial | Medium | Schema + PIR coverage done; volume + drift TBD
T031 | P3 | Data & Code Readiness | Review and resolve data/code intake issues | BOTH | BOTH | ABSA Data Owner | High | 5 | 2026-02-23 | 2026-02-27 |  | T029,T030 | Not Started | Planned | Medium | Triage process per model
T032 | P4 | Platform Foundation Build | Build AWS landing zone + core networking | EXL | EXL | Tech Lead | Critical | 10 | 2026-02-01 | 2026-02-06 |  | T014 | Not Started | Partial | Medium | Modules ready; apply on real accounts
T033 | P4 | Platform Foundation Build | Configure IAM roles, KMS keys, secrets | EXL | EXL | Tech Lead | Critical | 8 | 2026-02-06 | 2026-02-11 |  | T032 | Not Started | Partial | Medium | signing-foundation module ready
T034 | P4 | Platform Foundation Build | Set up ML compute platform for model runs | EXL | EXL | Tech Lead | Critical | 15 | 2026-02-12 | 2026-02-17 |  | T033 | Not Started | Planned | High | Choice: SFN+Lambda vs SageMaker (decision needed)
T035 | P4 | Platform Foundation Build | Create model registry + version control standards | EXL | EXL | Tech Lead | Critical | 5 | 2026-02-18 | 2026-02-23 |  | T033 | Done | Done | Low | registry-api FastAPI + DynamoDB
T036 | P4 | Platform Foundation Build | Set up feature metadata + lineage capture | EXL | EXL | Tech Lead | High | 8 | 2026-02-24 | 2026-03-01 |  | T035 | In Progress | Partial | Medium | PIR captures input lineage; output TBD
T037 | P4 | Platform Foundation Build | Set up CI/CD pipelines for deployment + rollback | EXL | EXL | Tech Lead | High | 10 | 2026-03-02 | 2026-03-07 |  | T032 | In Progress | Partial | Medium | GH Actions workflows in place
T038 | P4 | Platform Foundation Build | Create infrastructure-as-code templates | EXL | EXL | Tech Lead | High | 5 | 2026-03-07 | 2026-03-12 |  | T032 | Done | Done | Low | All terraform/ modules + per-env stacks
T039 | P4 | Platform Foundation Build | Set up observability, logging, alerts [Vishnu's Repo] | EXL | EXL | Tech Lead | High | 8 | 2026-03-13 | 2026-03-18 |  | T037 | In Progress | Partial | Medium | Audit emission done; dashboards TBD
T040 | P4 | Platform Foundation Build | Set up audit trail + evidence capture | EXL | EXL | Compliance Lead | Critical | 5 | 2026-03-19 | 2026-03-24 |  | T035 | Done | Done | Low | registry-api emits append-only audit
T041 | P4 | Platform Foundation Build | Validate platform readiness vs security controls [Vishnu's Repo] | BOTH | BOTH | ABSA Risk Owner | Critical | 5 | 2026-03-25 | 2026-03-30 |  | T040 | Done | Done | Low | docs/compliance/control-matrix.md
T042 | P5 | Controls, Security & Change Mgmt | Define change-request workflow + approval matrix | BOTH | BOTH | ABSA Risk Owner | High | 5 | 2026-02-01 | 2026-02-22 |  | T001 | In Progress | Partial | Medium | registry-api approval state machine
T043 | P5 | Controls, Security & Change Mgmt | Set up review process for medium/high-risk changes [Vishnu's Repo] | BOTH | BOTH | ABSA Risk Owner | High | 5 | 2026-02-22 | 2026-03-15 |  | T042 | In Progress | Partial | Medium | approve/retire routes + audit log
T044 | P5 | Controls, Security & Change Mgmt | Define peer review + promotion gates for production | BOTH | BOTH | Compliance Lead | High | 3 | 2026-03-15 | 2026-04-05 |  | T042 | Done | Done | Low | GH branch protection + drift gates + localstack-demo
T045 | P5 | Controls, Security & Change Mgmt | Document rollback requirements for planned changes | EXL | EXL | Compliance Lead | Medium | 3 | 2026-04-05 | 2026-04-26 |  | T044 | In Progress | Partial | Medium | Runbook structure exists; per-model TBD
T046 | P5 | Controls, Security & Change Mgmt | Set up release logging in agreed tracking tool | EXL | EXL | Compliance Lead | Medium | 3 | 2026-04-27 | 2026-05-18 |  | T040 | Done | Done | Low | Audit log via registry-api
T047 | P5 | Controls, Security & Change Mgmt | Confirm data retention and archival rules | BOTH | BOTH | ABSA Risk Owner | High | 3 | 2026-05-18 | 2026-06-08 |  | T042 | Not Started | Planned | Medium | S3 lifecycle policies
T048 | P5 | Controls, Security & Change Mgmt | Confirm secure access controls for dashboard endpoints | BOTH | BOTH | Compliance Lead | High | 3 | 2026-06-08 | 2026-06-29 |  | T042 | Not Started | Planned | Medium | After dashboard build (Phase 8)
T049 | P6 | Code Optimization & Pipeline Setup | Review developer code for production readiness | EXL | EXL | Tech Lead | Critical | 8 | 2026-03-01 | 2026-03-08 |  | T029,T034 | In Progress | Partial | Medium | code-intake validate --strict
T050 | P6 | Code Optimization & Pipeline Setup | Standardize and optimize model scoring code | EXL | EXL | Tech Lead | Critical | 15 | 2026-03-08 | 2026-03-15 |  | T025,T049 | Not Started | Planned | High | Per-package work; uses dev env access
T051 | P6 | Code Optimization & Pipeline Setup | Validate scoring logic against dev benchmarks | BOTH | BOTH | ABSA Model Owner | Critical | 8 | 2026-03-16 | 2026-03-23 |  | T050 | Not Started | Blocked | High | Reconciliation framework
T052 | P6 | Code Optimization & Pipeline Setup | Package scoring code for controlled deployment | EXL | EXL | Tech Lead | Critical | 5 | 2026-03-23 | 2026-03-30 |  | T051 | Done | Done | Low | Package contract spec (ADR-0010)
T053 | P6 | Code Optimization & Pipeline Setup | Create reusable scoring pipeline templates | EXL | EXL | Tech Lead | Critical | 8 | 2026-03-31 | 2026-04-07 |  | T034,T052 | Done | Done | Low | pipeline-factory ASL templates
T054 | P6 | Code Optimization & Pipeline Setup | Register models + pipeline versions in registry | EXL | EXL | Tech Lead | High | 3 | 2026-04-07 | 2026-04-14 |  | T035,T053 | Done | Done | Low | register-pipeline CLI (SigV4)
T055 | P6 | Code Optimization & Pipeline Setup | Set up model run schedules for approved cadence | BOTH | BOTH | ABSA Risk Owner | High | 3 | 2026-04-15 | 2026-04-22 |  | T006,T054 | Not Started | Planned | Medium | EventBridge schedules
T056 | P6 | Code Optimization & Pipeline Setup | Complete code intake validation + metadata capture [Vishnu's Repo] | EXL | EXL | Tech Lead | Critical | 3 | 2026-04-22 | 2026-04-29 |  | T049 | Done | Done | Low | code-intake generate-manifest
T057 | P7 | Group 1: First 2 Models | Prepare Group 1 onboarding plan | EXL | EXL | Tech Lead | Critical | 5 | 2026-04-01 | 2026-04-05 |  | T056 | Not Started | Planned | Medium | Per-model checklist
T058 | P7 | Group 1: First 2 Models | Run initial scoring for Group 1 models | EXL | EXL | Tech Lead | Critical | 5 | 2026-04-05 | 2026-04-09 |  | T057 | Not Started | Blocked | High | Needs real ABSA accounts + data
T059 | P7 | Group 1: First 2 Models | Reconcile Group 1 outputs with benchmarks | BOTH | BOTH | ABSA Model Owner | Critical | 5 | 2026-04-10 | 2026-04-14 |  | T058 | Not Started | Blocked | High | Byte/value comparison vs ABSA golden
T060 | P7 | Group 1: First 2 Models | Resolve defects identified during initial output testing | BOTH | BOTH | ABSA Model Owner | Critical | 8 | 2026-04-15 | 2026-04-19 |  | T059 | Not Started | Planned | High | Defect log + retest cadence
T061 | P7 | Group 1: First 2 Models | Complete PIR for Group 1 models | BOTH | BOTH | ABSA Risk Owner | Critical | 5 | 2026-04-20 | 2026-04-24 |  | T060 | Not Started | Planned | High | Post-Implementation Review
T062 | P7 | Group 1: First 2 Models | MILESTONE: Obtain sign-off for Group 1 | ABSA | ABSA | ABSA Risk Owner | Critical | 2 | 2026-04-25 | 2026-04-29 |  | T061 | Not Started | Blocked | High | *** GATE TO GROUP 2 ***
T063 | P8a | Group 2: Remaining 8 Models | Prepare onboarding plan for Group 2 | EXL | EXL | Tech Lead | Critical | 5 | 2026-05-01 | 2026-05-11 |  | T062 | Not Started | Planned | Medium | Reuses Group 1 lessons + templates
T064 | P8a | Group 2: Remaining 8 Models | Run onboarding and scoring for Group 2 | EXL | EXL | Tech Lead | Critical | 20 | 2026-05-11 | 2026-05-21 |  | T063 | Not Started | Planned | Medium | Each uses pipeline template
T065 | P8a | Group 2: Remaining 8 Models | Reconcile Group 2 outputs with benchmarks | BOTH | BOTH | ABSA Model Owner | Critical | 10 | 2026-05-21 | 2026-05-31 |  | T064 | Not Started | Planned | Medium | Same framework as Group 1
T066 | P8a | Group 2: Remaining 8 Models | Resolve defects during Group 2 testing | BOTH | BOTH | ABSA Model Owner | Critical | 10 | 2026-05-31 | 2026-06-10 |  | T065 | Not Started | Planned | Medium
T067 | P8a | Group 2: Remaining 8 Models | Complete PIR for Group 2 models | BOTH | BOTH | ABSA Risk Owner | Critical | 8 | 2026-06-10 | 2026-06-20 |  | T066 | Not Started | Planned | Medium
T068 | P8a | Group 2: Remaining 8 Models | MILESTONE: Obtain sign-off for Group 2 | ABSA | ABSA | ABSA Risk Owner | Critical | 2 | 2026-06-20 | 2026-06-30 |  | T067 | Not Started | Planned | Medium | Closes initial-onboarding scope
T069 | P8b | Dashboards & Delivery | Agree dashboard views, recipients, access levels | BOTH | BOTH | ABSA Risk Owner | High | 3 | 2026-05-01 | 2026-05-09 |  | T048 | Not Started | Planned | Low | Who sees what, when
T070 | P8b | Dashboards & Delivery | Build monitoring dashboard for runs + exceptions | EXL | EXL | Tech Lead | High | 10 | 2026-05-09 | 2026-05-17 |  | T069 | Not Started | Planned | Medium | CloudWatch + Grafana or equivalent
T071 | P8b | Dashboards & Delivery | Configure notifications + alert routing for failures | BOTH | BOTH | Tech Lead | High | 3 | 2026-05-18 | 2026-05-26 |  | T070 | Not Started | Planned | Medium | SNS / PagerDuty / Slack
T072 | P8b | Dashboards & Delivery | Validate dashboard for inputs, outputs, failures | BOTH | BOTH | ABSA Risk Owner | High | 3 | 2026-05-26 | 2026-06-03 |  | T070 | Not Started | Planned | Low
T073 | P8b | Dashboards & Delivery | Set up secure output delivery process to ABSA | EXL | EXL | Compliance Lead | Critical | 5 | 2026-06-04 | 2026-06-12 |  | T018 | In Progress | Partial | Medium | S3 replication path
T074 | P8b | Dashboards & Delivery | Confirm operational runbooks + support contacts | BOTH | BOTH | Program Mgr | High | 3 | 2026-06-12 | 2026-06-20 |  | T070 | In Progress | Partial | Medium | docs/runbooks/ started
T075 | P8b | Dashboards & Delivery | Publish runbooks + operating procedures + handover | EXL | EXL | Program Mgr | Critical | 5 | 2026-06-21 | 2026-06-29 |  | T074 | In Progress | Partial | Medium | Demo + key-rotation runbooks done
T076 | P9a | Steady State Support | Start scheduled production scoring | EXL | EXL | Tech Lead | Critical | 5 | 2026-07-01 | 2026-07-22 |  | T068,T075 | Not Started | Planned | Medium
T077 | P9a | Steady State Support | Monitor daily, weekly, monthly scoring runs | EXL | EXL | Tech Lead | High | 0 | 2026-07-22 | 2026-08-12 |  | T076 | Not Started | Planned | Low | Ongoing
T078 | P9a | Steady State Support | Track run failures + coordinate recovery actions | BOTH | BOTH | ABSA Risk Owner | Critical | 0 | 2026-08-12 | 2026-09-02 |  | T076 | Not Started | Planned | Medium | Incident response process
T079 | P9a | Steady State Support | Maintain audit trail for every scoring run and delivery | EXL | EXL | Compliance Lead | Critical | 0 | 2026-09-03 | 2026-09-24 |  | T076 | Done | Done | Low | registry-api audit + signed manifests
T080 | P9a | Steady State Support | Review data drift, anomalies, scoring exceptions | BOTH | BOTH | ABSA Risk Owner | High | 0 | 2026-09-24 | 2026-10-15 |  | T076 | Not Started | Planned | Medium | *** Need Comment: drift framework ***
T081 | P9a | Steady State Support | Manage approved changes | BOTH | BOTH | ABSA Risk Owner | High | 0 | 2026-10-16 | 2026-11-06 |  | T076 | Not Started | Planned | Medium | *** Need Comment: change-mgmt cadence ***
T082 | P9a | Steady State Support | Refresh access, whitelists, secrets when required | BOTH | BOTH | Compliance Lead | High | 0 | 2026-11-06 | 2026-11-27 |  | T076 | Not Started | Planned | Medium | *** Need Comment: rotation cadence ***
T083 | P9a | Steady State Support | Archive model data + outputs as per retention rules | EXL | EXL | Compliance Lead | Medium | 0 | 2026-11-27 | 2026-12-18 |  | T076 | Not Started | Planned | Low | S3 lifecycle policies
T084 | P9a | Steady State Support | Conduct periodic service review with ABSA | BOTH | BOTH | ABSA Risk Owner | High | 0 | 2026-12-19 | 2027-01-09 |  | T076 | Not Started | Planned | Low | Quarterly cadence
T085 | P9a | Steady State Support | Handle operational incidents + secondary support | EXL | EXL | Program Mgr | Critical | 0 | 2027-01-09 | 2027-01-30 |  | T076 | Not Started | Planned | Medium
T086 | P9b | New Model Onboarding | Review each new onboarding request + classify model type | BOTH | BOTH | Program Mgr | High | 2 | 2026-07-01 | 2026-08-05 |  | T068 | Not Started | Planned | Low | Standard-batch / Scalable-batch / Realtime
T087 | P9b | New Model Onboarding | Collect approved artefacts, inputs, benchmark outputs | ABSA | ABSA | ABSA Model Owner | High | 5 | 2026-08-05 | 2026-09-09 |  | T086 | Not Started | Planned | Medium | Same intake contract
T088 | P9b | New Model Onboarding | Reuse existing template for subsequent model of same type | EXL | EXL | Tech Lead | Medium | 3 | 2026-09-10 | 2026-10-15 |  | T087 | Done | Done | Low | pipeline-factory regenerates
T089 | P9b | New Model Onboarding | Build type-specific controls for new model category | EXL | EXL | Tech Lead | Medium | 10 | 2026-10-16 | 2026-11-20 |  | T087 | Not Started | Planned | Medium | If new tier introduced
T090 | P9b | New Model Onboarding | Run validation, scoring, PIR for each newly onboarded model | BOTH | BOTH | ABSA Model Owner | High | 10 | 2026-11-20 | 2026-12-25 |  | T088 | Not Started | Planned | Medium | Same Group 1/2 framework
T091 | P9b | New Model Onboarding | Add approved new models to registry + run schedule | EXL | EXL | Tech Lead | Medium | 2 | 2026-12-26 | 2027-01-30 |  | T090 | Done | Done | Low | register-pipeline + EventBridge
T101 | M1 | Jenkins Migration: Foundation | ADR-0011 drafted + committed | EXL | EXL | Tech Lead | Critical | 1 | 2026-06-08 | 2026-06-11 |  |  | Done | Done | Low | Status: Proposed
T102 | M1 | Jenkins Migration: Foundation | Shared library 'absa-ci' skeleton + 5 example Jenkinsfiles | EXL | EXL | Tech Lead | Critical | 2 | 2026-06-09 | 2026-06-12 |  | T101 | Done | Done | Low | ci/jenkins/ committed
T103 | M1 | Jenkins Migration: Foundation | ABSA confirms Jenkins identity model (IRSA on EKS preferred) | ABSA | ABSA | ABSA Architect | Critical | 3 | 2026-06-10 | 2026-06-13 |  | T101 | Not Started | Blocked | High | *** GATING — unblocks every M2 task ***
T104 | M1 | Jenkins Migration: Foundation | Stand up Jenkins sandbox + register absa-ci shared library | EXL | EXL | Tech Lead | Critical | 5 | 2026-06-11 | 2026-06-14 |  | T103 | Not Started | Blocked | Medium | Sandbox proves library wiring before any real workflow flips
T105 | M1 | Jenkins Migration: Foundation | Run python-validate.Jenkinsfile end-to-end in sandbox | EXL | EXL | Tech Lead | High | 2 | 2026-06-12 | 2026-06-14 |  | T104 | Not Started | Blocked | Medium | Proving ground — confirms commit-status reporting works
T106 | M1 | Jenkins Migration: Foundation | Stamp ADR-0011 Status: Accepted after sandbox proves out | EXL | EXL | Tech Lead | High | 1 | 2026-06-13 | 2026-06-14 |  | T105 | Not Started | Blocked | Low
T107 | M2 | Jenkins Migration: AWS-touching | signing-foundation Terraform: identity_provider variable | EXL | EXL | Tech Lead | Critical | 3 | 2026-06-15 | 2026-06-18 |  | T103 | Not Started | Blocked | Medium | Trust both providers during cutover
T108 | M2 | Jenkins Migration: AWS-touching | Apply signing-foundation update to exl-prod stack | EXL | EXL | Tech Lead | Critical | 1 | 2026-06-17 | 2026-06-20 |  | T107 | Not Started | Blocked | Medium
T109 | M2 | Jenkins Migration: AWS-touching | Port publish-signing-key.yml -> Jenkinsfile | EXL | EXL | Tech Lead | High | 2 | 2026-06-20 | 2026-06-23 |  | T108 | Not Started | Blocked | Low | Held in M1 — identity model decided here
T110 | M2 | Jenkins Migration: AWS-touching | Validate pipeline-factory.Jenkinsfile against real AWS | EXL | EXL | Tech Lead | Critical | 3 | 2026-06-22 | 2026-06-25 |  | T108 | Not Started | Blocked | High | Signature byte-equivalence GHA vs Jenkins
T111 | M2 | Jenkins Migration: AWS-touching | Parallel-run GHA + Jenkins for 1 week | EXL | EXL | Tech Lead | High | 5 | 2026-06-25 | 2026-06-28 |  | T110 | Not Started | Blocked | Medium | Compare digests, signatures, manifests byte-by-byte
T112 | M3 | Jenkins Migration: Cutover | Flip GitHub branch protection to Jenkins commit statuses | EXL | EXL | Tech Lead | Critical | 1 | 2026-06-29 | 2026-07-02 |  | T111 | Not Started | Blocked | High | One-way step; rollback = re-add GHA contexts
T113 | M3 | Jenkins Migration: Cutover | Disable GHA workflows (.github/workflows/*.disabled.yml) | EXL | EXL | Tech Lead | High | 1 | 2026-06-30 | 2026-07-03 |  | T112 | Not Started | Blocked | Low | Keep one release for rollback safety
T114 | M3 | Jenkins Migration: Cutover | Sweep ADR-0003, ADR-0009, runbooks, technical-overview | EXL | EXL | Tech Lead | Medium | 2 | 2026-07-02 | 2026-07-05 |  | T112 | Not Started | Blocked | Low | ADRs cross-referenced in M1; full sweep here
T115 | M3 | Jenkins Migration: Cutover | Promote compliance matrix Phase 3 rows from Proposed -> Live | EXL | EXL | Compliance Lead | High | 1 | 2026-07-03 | 2026-07-05 |  | T112 | Not Started | Blocked | Low | Auditor evidence URLs point to Jenkins builds

## Phase Summary
Phase Summary
Phase | Months | Title | Task count (formula) | Effort total (formula) | Critical milestones | Status snapshot
P1 | M1 | Project Governance & Scope |  |  | SPOCs identified · scope sign-off
P2 | M1-2 | Architecture, Access & Connectivity |  |  | ABSA architecture sign-off · IAM trust established
P3 | M1-2 | Data & Code Readiness |  |  | First model code + data + benchmarks in intake pipeline
P4 | M2-3 | Platform Foundation Build |  |  | Real AWS accounts deployed via Terraform
P5 | M2-6 | Controls, Security & Change Mgmt |  |  | Cross-cutting; runs alongside Phases 4-8
P6 | M3-4 | Code Optimization & Pipeline Setup |  |  | Pipeline template registered for first model
P7 | M4 | Group 1: First 2 Models |  |  | *** ABSA SIGN-OFF — BIGGEST MILESTONE ***
P8a | M5-6 | Group 2: Remaining 8 Models |  |  | All 10 models in production scoring
P8b | M5-6 | Dashboards & Delivery Readiness |  |  | Dashboards live; runbooks published
P9a | M7+ | Steady State Support |  |  | Quarterly reviews; ongoing ops
P9b | M7+ | New Model Onboarding |  |  | Template-driven new model ramp
M1 | Jun W2 | Jenkins Migration: Foundation |  |  | ADR-0011 accepted · sandbox proves library
M2 | Jun W3-4 | Jenkins Migration: AWS-touching |  |  | signing-foundation supports both providers · parallel run
M3 | Jul W1 | Jenkins Migration: Cutover |  |  | Branch protection flipped · GHA retired

## Milestones & Gates
Milestones & Gates
Milestone ID | Description | Target Date | Owner | Status | Gate Criteria
M01 | Project kickoff complete + SPOCs identified | 2026-01-15 | Program Mgr | Not Started | Signed kickoff minutes; SPOC names on file
M02 | Scope + 10-model delivery plan signed off | 2026-01-31 | Steering Committee | Not Started | Scope doc approved; sequencing locked
M03 | Architecture sign-off from ABSA | 2026-02-15 | ABSA Architect | Blocked | Architecture review board minutes + decision log
M04 | EXL AWS landing zone live + IAM trust established | 2026-02-28 | EXL Cloud Eng | Partial | Real account IDs provisioned; cross-account roles verifiable
M05 | First ABSA package transferred + validated | 2026-02-28 | Tech Lead | Blocked | code-intake validate exits 0; manifest signed
M06 | Platform foundation built + security control sign-off | 2026-03-31 | Tech Lead | Partial | Control matrix evidence + readiness review
M07 | Code optimization complete + pipeline templates live | 2026-04-15 | Tech Lead | Planned | Pipeline template registered for first model type
M08 | *** GROUP 1 SIGN-OFF (2 MODELS) *** | 2026-04-30 | ABSA Risk Owner | Blocked | PIR complete; benchmark reconciliation passes
M09 | *** GROUP 2 SIGN-OFF (REMAINING 8 MODELS) *** | 2026-06-30 | ABSA Risk Owner | Planned | All 10 models reconciled; PIR sign-off
M10 | Dashboards + delivery handover published | 2026-06-30 | Program Mgr | Planned | Runbooks published; support contacts confirmed
M11 | Steady-state go-live | 2026-07-01 | Program Mgr | Planned | First quarterly review scheduled; ops contacts staffed
M12 | Jenkins identity model confirmed (IRSA vs instance) | 2026-06-14 | ABSA Cloud Platform | Blocked | *** Gates entire Sprint M2 of Jenkins migration ***
M13 | GHA retired; Jenkins is the sole CI gate | 2026-07-05 | EXL DevOps | Planned | Branch protection flipped; .disabled.yml retained 1 release

## Risk Register
Risk Register
Risk ID | Description | Phase | Probability (1-5) | Impact (1-5) | Score (P*I) | Mitigation | Owner
R01 | ABSA account onboarding (real AWS account IDs + IAM principals) delayed | P2/P4 | 4 | 5 |  | Pre-stage Terraform + use LocalStack demo to keep CI green; escalate to Steering by end of Month 1 | ABSA Architect
R02 | ABSA-side internal cloud approvals slip past Month 2 | P2 | 3 | 5 |  | Start approval process before kickoff; weekly check-in with ABSA cloud team | ABSA Architect
R03 | Group 1 sign-off (Month 4) slips, cascading into Group 2 and steady state | P7 | 3 | 5 |  | Use Group 1 onboarding plan as dress rehearsal; pre-stage Group 2 templates | ABSA Risk Owner
R04 | ML compute platform choice (SFN+Lambda vs SageMaker) blocks Phase 4 build | P4 | 3 | 4 |  | Decision required by end of Month 2; architecture review board agenda item | Tech Lead
R05 | Benchmark reconciliation discrepancies require model code rewrite | P6/P7 | 3 | 4 |  | Validate scoring logic incrementally during code optimization; record per-feature deltas | EXL ML Eng
R06 | Cross-account encrypted transfer path not validated end-to-end before Phase 4 | P2 | 2 | 4 |  | Phase-gate Phase 4 on Phase 2 transfer validation; LocalStack demo verifies the shape today | EXL Cloud Eng
R07 | SSO federation testing reveals incompatible identity provider config | P2 | 2 | 3 |  | Joint test in Month 2; fall back to direct IAM if SSO blocks | EXL Cloud Eng
R08 | Data quality issues (drift, schema mismatch) in initial intake delay code optimization | P3/P6 | 3 | 4 |  | Run code-intake validate on first arrival; reject + return to ABSA immediately | EXL Eng
R09 | PIR review reveals input variable misalignment, requires re-scope | P7 | 2 | 5 |  | Lock input variables in Phase 1; PIR rehearsal during Group 1 | ABSA Risk Owner
R10 | Production scoring SLA cannot be met on selected ML compute platform | P9a | 2 | 4 |  | Load-test in Phase 7 before Group 1 go-live | EXL ML Eng
R11 | KMS signing key compromise during operations | P9a | 1 | 5 |  | Rotation runbook (docs/runbooks/kms-key-rotation.md) in place; quarterly drill | Compliance Lead
R12 | Change management workflow not finalized before first production change | P5 | 2 | 4 |  | Use registry-api approval state machine as baseline; document workflow by Month 3 | Compliance Lead
R13 | ABSA does not run Jenkins on EKS — IRSA path closed, fall back to EC2 instance profile | M1 | 3 | 3 |  | ADR-0011 already documents the EC2 fallback path; awsLogin step handles both modes; identified as a known fallback rather than a blocker | Tech Lead
R14 | Jenkins shared library Groovy has runtime bugs that only surface against a real Jenkins instance | M1 | 3 | 3 |  | Sprint M1 sandbox proves library before Sprint M2 starts; 5 example Jenkinsfiles share the same shared-library surface so bugs fail consistently | EXL DevOps
R15 | Signature byte-equivalence fails between GHA and Jenkins runs (canonical_json sensitivity to env) | M2 | 2 | 5 |  | Parallel-run week explicitly compares manifest digests; canonical_json is deterministic by spec but Python version drift could shift behaviour | Tech Lead

## Open Decisions
Open Decisions
Decision ID | Description | Phase Impact | Owner | Due Date | Impact if not decided
D01 | Data drift detection framework: which metrics (PSI / KL-divergence / feature-distribution shift)? What window? Manual review vs automated alerting? | P9a | ABSA Risk Owner + EXL ML Eng | 2026-05-31 | Cannot ship dashboards (Phase 8b) without agreed drift metrics. Steady state ops lacks anomaly framework.
D02 | Change management cadence: production-change approval — registry's approve/retire state machine or separate Jira workflow? | P5/P9a | Compliance Lead + ABSA Risk Owner | 2026-03-31 | Group 1 production releases blocked without an agreed change workflow.
D03 | Access / secret rotation cadence (IAM principals, registrar tokens, dashboard access). KMS signing key has a runbook; the rest don't. | P5/P9a | Compliance Lead | 2026-04-30 | Audit findings if rotation cadence not documented before steady state.
D04 | ML compute platform: Step Functions + Lambda OR SageMaker Pipelines? | P4 | Tech Lead + Architecture Board | 2026-02-28 | Blocks Phase 4 ML compute setup. Affects pipeline-factory ASL renderer scope.
D05 | Real-time scoring tier SLA: what's the response budget? Lambda+APIGW / ECS Fargate / SageMaker endpoint? | P4 | Tech Lead + ABSA Architect | 2026-03-31 | Realtime ASL template is currently a placeholder. SLA drives the implementation choice.
D06 | Data-movement choice: S3 cross-account replication or SFTP transfer for scoring inputs/outputs? | P2 | ABSA Architect + EXL Cloud Eng | 2026-02-15 | Blocks Phase 2 secure transfer build. Both directions need this lock.
D07 | Multi-region: is the platform single-region (eu-west-1) or multi-region from day 1? | P4 | ABSA Architect | 2026-03-15 | Affects KMS replica strategy, signing-foundation scope, runbook structure.
D08 | Dashboard hosting: Grafana / CloudWatch native / QuickSight / something ABSA-supplied? | P8b | Program Mgr + ABSA Risk Owner | 2026-04-30 | Dashboard build (Phase 8b) blocked without tool decision.
D09 | Output delivery format to ABSA: signed S3 bucket / SFTP push / API pull? | P8b | ABSA Architect + EXL Cloud Eng | 2026-04-30 | Cannot finalize delivery runbook.

## Dashboard
Program Dashboard
Tasks by Delivery Status |  |  | Tasks by Owner
Owner | Count |  | Owner | Count
Done |  |  | BOTH
Partial |  |  | EXL
Planned |  |  | ABSA
Blocked |  |  | EXL (ABSA Side)
In Progress
Not Started
Total
Tasks by Phase
Phase | Title | Tasks | Effort (d) | Blocked | Done
P1 | Governance
P2 | Architecture
P3 | Data/Code Readiness
P4 | Platform Foundation
P5 | Controls
P6 | Code Optimization
P7 | Group 1 (2 models)
P8a | Group 2 (8 models)
P8b | Dashboards
P9a | Steady State
P9b | New Model Onboarding
M1 | Jenkins: Foundation
M2 | Jenkins: AWS-touching
M3 | Jenkins: Cutover