## README
ABSA x EXL - Agile Sprint Plan (in-depth)
Anchoring: Sprint 1 = Mon 2026-06-15. 12 sprints x 2 weeks ~ 6 months.
Group 1 ABSA sign-off targeted end of Sprint 8 (2026-10-02). All 10 models live by end S11; Group 2 sign-off + go-live end S12.
TEAM SHAPE - 8 people (right-sized for a solid 12 sprints):
- 2 AWS/MLOps engineers split the foundation: AWS (Foundation & Infra) + AWS2 (Platform, Compute &
MLOps). The total AWS workload is only ~62 effort-days, so 2 carry it at a healthy ~75% peak;
a 3rd was dropped as under-utilized (it sat idle most of S8-S12).
- 3 SAS developers: two from S1 run Group 1 models 1 & 2 IN PARALLEL (kills bus-factor-of-one on
the proof); a third onboards S8 for Group 2.
Group 2 (8 models) is compressed into S9-S11 (3 models/sprint, then 2) so ALL 10 are live by end S11,
leaving S12 entirely for hardening, sign-off, and handover - not a race to finish models.
The S5 capacity review (T-1301) confirms the 3rd SAS dev + plans AWS ramp-down after foundation.
Team & capacity (effort-days per 2-week sprint = 10 working days x 0.8 focus factor):
AWS - AWS/MLOps Eng #1 (Foundation & Infra) - 8.0 d/sprint
AWS2 - AWS/MLOps Eng #2 (Platform, Compute & MLOps) - 8.0 d/sprint
DE - Data Engineer - 8.0 d/sprint
SAS - SAS Developer #1 (Model 1 / Group 2) - 8.0 d/sprint
SAS2 - SAS Developer #2 (Model 2 / Group 2) - 8.0 d/sprint
SAS3 - SAS Developer #3 (Group 2) - 8.0 d/sprint FROM SPRINT 8 (0 before)
DevOps - DevOps Engineer - 8.0 d/sprint
TL - Tech Lead (Vishnu) - 6.0 d/sprint (splits with program mgmt)
COST LEVER: AWS2 is loaded S1-S7 (platform + compute) then light. After S7 it can ramp down or
redeploy to MLOps/optimization work - planned at the S5 review (RAID ASM-02). AWS #1 carries the
Group 2 pipeline-deploy tail S9-S11.
Only DevOps is un-doubled; watch its S2 (7.0) and S6 (6.5) peaks (RAID RISK-07).
How to use:
1. 'Backlog' is the source of truth: EPIC -> Story -> Task with role, sprint, estimate, points, MoSCoW.
Import into Jira (CSV) or mirror manually; Sprint 1-8 base task IDs are stable.
2. 'Sprint Plan' = goal + milestone per sprint + per-role load (formula-driven), 9 role columns.
3. 'Role Load' = capacity heat grid. Grey = off-team (SAS3 pre-S8). Red = overloaded (must re-plan).
4. 'Per-Model Tracker' = the 10 models x onboarding stages; the heart of the program.
5. 'Governance & Cadence' = ceremonies + decision/sign-off checkpoints with target sprints.
6. 'RAID Log' = risks, assumptions, issues, dependencies (incl. the 8 ABSA dependencies).
7. Update Status on Backlog as work moves; Dashboard recalculates.
Definition of Ready (a story may enter a sprint when):
- Acceptance criteria written; dependencies identified; estimate agreed; no unresolved ABSA blocker for that sprint.
Definition of Done (a task is done when):
- Merged to main; CI green; docs updated if behaviour changed; acceptance criteria met; demoed on review Friday.
Context: the platform (registry, pipeline-factory, signer, code-intake, LocalStack demo) is already built and
regression-tested - see docs/phase-3-closeout.md. This plan covers real-AWS deployment, the Jenkins CI
migration, onboarding 10 SAS models, security/compliance hardening, testing/UAT, and go-live.

## Backlog
Backlog - EPIC / Story / Task
Type | ID | Parent | Epic | Title | Role | Sprint | Est (d) | Pts | MoSCoW | Depends On | Blocked On (ABSA) | Status | Acceptance / Notes
EPIC | E01 |  | E01 | Team Onboarding & Governance - Everyone productive in week 1: repo green locally, board live, ABSA dependency register running. | TL | S1
Story | ST-0101 | E01 | E01 | Environment & platform onboarding |  | S1 | 7 | 8 | Must |  |  |  | All engineers: 278-test suite green + `make demo` exit 0 locally; walkthrough attended.
Task | T-0101 | ST-0101 | E01 | Clone repo, uv sync, run full 278-test suite locally | AWS | S1 | 0.5 |  |  |  |  | Planned
Task | T-0102 | ST-0101 | E01 | Clone repo, uv sync, run full 278-test suite locally | DE | S1 | 0.5 |  |  |  |  | Planned
Task | T-0103 | ST-0101 | E01 | Clone repo, uv sync, run full 278-test suite locally | SAS | S1 | 0.5 |  |  |  |  | Planned
Task | T-0104 | ST-0101 | E01 | Clone repo, uv sync, run full 278-test suite locally | DevOps | S1 | 0.5 |  |  |  |  | Planned
Task | T-0105 | ST-0101 | E01 | Run `make demo` (LocalStack chain) green locally | AWS | S1 | 0.5 |  |  | T-0101 |  | Planned
Task | T-0106 | ST-0101 | E01 | Run `make demo` (LocalStack chain) green locally | DE | S1 | 0.5 |  |  | T-0102 |  | Planned
Task | T-0107 | ST-0101 | E01 | Run `make demo` (LocalStack chain) green locally | SAS | S1 | 0.5 |  |  | T-0103 |  | Planned
Task | T-0108 | ST-0101 | E01 | Run `make demo` (LocalStack chain) green locally | DevOps | S1 | 0.5 |  |  | T-0104 |  | Planned
Task | T-0101b | ST-0101 | E01 | Clone repo, uv sync, tests green locally | AWS2 | S1 | 0.5 |  |  |  |  | Planned
Task | T-0103b | ST-0101 | E01 | Clone repo, uv sync, tests green locally | SAS2 | S1 | 0.5 |  |  |  |  | Planned
Task | T-0105b | ST-0101 | E01 | Run `make demo` green locally | AWS2 | S1 | 0.5 |  |  | T-0101b |  | Planned
Task | T-0107b | ST-0101 | E01 | Run `make demo` green locally | SAS2 | S1 | 0.5 |  |  | T-0103b |  | Planned
Task | T-0109 | ST-0101 | E01 | Host architecture walkthrough: chain-of-custody, repo tour, ADR index | TL | S1 | 1 |  |  |  |  | Planned | Record for future joiners
Story | ST-0102 | E01 | E01 | Agile working agreement & board |  | S1 | 2 | 2 | Must |  |  |  | Jira board mirrors this backlog; DoR/DoD + ceremony calendar published.
Task | T-0110 | ST-0102 | E01 | Stand up Jira/ADO board; import this EPIC/Story/Task tree | TL | S1 | 1 |  |  |  |  | Planned | Backlog sheet is the import source
Task | T-0111 | ST-0102 | E01 | Publish Definition of Ready/Done + PR / branch-protection workflow | TL | S1 | 0.5 |  |  |  |  | Planned
Task | T-0112 | ST-0102 | E01 | Ceremony calendar: standup, planning, review+demo, retro | TL | S1 | 0.5 |  |  |  |  | Planned
Story | ST-0103 | E01 | E01 | ABSA dependency management |  | S1 | 1 | 1 | Must |  |  |  | 8-item ask-list sent; weekly chase cadence running with named SPOC.
Task | T-0113 | ST-0103 | E01 | Send 8-item dependency ask-list to ABSA SPOC | TL | S1 | 0.5 |  |  |  |  | Planned | Accounts, IAM, SAS runtime, PIR, data movement, CAB/IVU, network, model docs
Task | T-0114 | ST-0103 | E01 | Stand up weekly dependency-chase cadence + escalation path | TL | S1 | 0.5 |  |  | T-0113 |  | Planned
EPIC | E02 |  | E02 | CI/CD on Existing Jenkins - Migrate all 6 CI gates from GitHub Actions to the standalone Jenkins per ADR-0011; retire GHA. | DevOps | S1-S3
Story | ST-0201 | E02 | E02 | Jenkins discovery & identity decision |  | S1 | 2.5 | 3 | Must |  |  |  | Topology documented; auth path chosen; ADR-0011 amended.
Task | T-0201 | ST-0201 | E02 | Document Jenkins topology: host, agents, executors, plugins, versions | DevOps | S1 | 1 |  |  |  |  | Planned | Standalone instance already running
Task | T-0202 | ST-0201 | E02 | Choose AWS auth path: instance profile / OIDC IdP plugin / keys+rotation | DevOps | S1 | 1 |  |  | T-0201 |  | Planned | Drives signing-foundation trust policy
Task | T-0203 | ST-0201 | E02 | Amend ADR-0011 with the standalone-Jenkins identity decision | TL | S1 | 0.5 |  |  | T-0202 |  | Planned
Story | ST-0202 | E02 | E02 | Shared library proving ground |  | S1-S2 | 4.5 | 5 | Must |  |  |  | absa-ci registered; ci/python-validate status visible on a GitHub PR.
Task | T-0204 | ST-0202 | E02 | Register absa-ci as Global Pipeline Library | DevOps | S1 | 0.5 |  |  | T-0201 |  | Planned | ci/jenkins/ path in this repo
Task | T-0205 | ST-0202 | E02 | Create multibranch job for python-validate; first run | DevOps | S1 | 1 |  |  | T-0204 |  | Planned
Task | T-0206 | ST-0202 | E02 | Verify ci/python-validate commit status lands on a GitHub PR | DevOps | S1 | 1 |  |  | T-0205 |  | Planned | Branch-protection sandbox check
Task | T-0207 | ST-0202 | E02 | Fix shared-library Groovy issues surfaced by first runs | DevOps | S2 | 2 |  |  | T-0206 |  | Planned | publishChecks plugin quirks, PATH handling
Story | ST-0203 | E02 | E02 | No-AWS pipelines live |  | S2 | 5 | 5 | Must |  |  |  | code-intake, terraform-validate, localstack-demo jobs green on Jenkins.
Task | T-0208 | ST-0203 | E02 | code-intake job live | DevOps | S2 | 0.5 |  |  | T-0207 |  | Planned
Task | T-0209 | ST-0203 | E02 | terraform-validate job live (docker tflint/tfsec/checkov/gitleaks) | DevOps | S2 | 1.5 |  |  | T-0207 |  | Planned
Task | T-0210 | ST-0203 | E02 | localstack-demo job live (Docker on agent, 0/1/2/3 exit-code gate) | DevOps | S2 | 2 |  |  | T-0207 |  | Planned | Needs Docker socket on agent
Task | T-0211 | ST-0203 | E02 | Wire platform secrets into Jenkins credentials store | DevOps | S2 | 1 |  |  | T-0202 |  | Planned | Secrets Manager-backed if reachable
Story | ST-0204 | E02 | E02 | AWS-touching pipelines + cutover |  | S3 | 6.5 | 8 | Must |  |  |  | sign/register green vs real AWS; 1-week parallel run byte-identical; branch protection flipped; GHA disabled.
Task | T-0212 | ST-0204 | E02 | pipeline-factory sign+register stages green against real AWS | DevOps | S3 | 2 |  |  | T-0309,T-0211 |  | Planned
Task | T-0213 | ST-0204 | E02 | publish-signing-key job | DevOps | S3 | 1 |  |  | T-0310 |  | Planned
Task | T-0214 | ST-0204 | E02 | 1-week GHA-vs-Jenkins parallel run; byte-equivalence report | DevOps | S3 | 2 |  |  | T-0212 |  | Planned | Compare manifest digests + signatures
Task | T-0215 | ST-0204 | E02 | Flip branch protection to Jenkins contexts; GHA -> *.disabled.yml | DevOps | S3 | 0.5 |  |  | T-0214 |  | Planned
Task | T-0216 | ST-0204 | E02 | Docs sweep: ADR-0003/0009 final edits; control-matrix rows -> Live | TL | S3 | 1 |  |  | T-0215 |  | Planned
EPIC | E03 |  | E03 | AWS Foundation (Real Accounts) - Bootstrap real EXL accounts, landing zone, signing foundation, registry-on-Lambda, replication path. Split across 2 AWS engineers: Foundation & Infra (AWS), Platform/Compute/MLOps (AWS2). | AWS x2 | S1-S4
Story | ST-0301 | E03 | E03 | Account bootstrap & state backends |  | S1-S2 | 7 | 8 | Must |  |  |  | CloudTrail/GuardDuty/SecurityHub live in 3 EXL accounts; TF state backends operational.
Task | T-0301 | ST-0301 | E03 | Module/stack review: gap notes vs real-AWS apply | AWS | S1 | 2 |  |  |  |  | Planned | terraform/ + account-bootstrap
Task | T-0302 | ST-0301 | E03 | tfvars templates per env (awaiting account IDs) | AWS | S1 | 1 |  |  | T-0301 |  | Planned
Task | T-0303 | ST-0301 | E03 | State backend design: S3 + DynamoDB locks per account | AWS | S1 | 1 |  |  | T-0301 |  | Planned
Task | T-0304 | ST-0301 | E03 | Apply account-bootstrap to exl-dev/stg/prod | AWS | S2 | 2 |  |  | T-0302 | ABSA: account IDs | Planned | CloudTrail, GuardDuty, SecurityHub, CIS alarms
Task | T-0305 | ST-0301 | E03 | Apply state backends | AWS | S2 | 1 |  |  | T-0304 |  | Planned
Story | ST-0302 | E03 | E03 | Landing zone & connectivity |  | S2-S3 | 6 | 8 | Must |  |  |  | Landing zone applied; network path to ABSA implemented; IPs whitelisted.
Task | T-0306 | ST-0302 | E03 | Apply landing-zone module (dev first) | AWS | S2 | 2 |  |  | T-0304 |  | Planned
Task | T-0307 | ST-0302 | E03 | Implement network connectivity per ABSA decision | AWS | S3 | 3 |  |  | T-0306 | ABSA: network choice | Planned | VPC peering / TGW / PrivateLink
Task | T-0308 | ST-0302 | E03 | IP whitelisting coordination with ABSA network team | AWS | S2 | 1 |  |  | T-0306 | ABSA: network choice | Planned
Story | ST-0303 | E03 | E03 | Signing foundation live |  | S2-S4 | 4.5 | 5 | Must |  |  |  | KMS CMK in exl-prod; PEM published; cross-account verify passes with ABSA principal.
Task | T-0309 | ST-0303 | E03 | identity_provider variable in signing-foundation TF (per T-0202) | AWS2 | S2 | 2 |  |  | T-0202 |  | Planned | Supports github_actions ¦ jenkins variants during cutover
Task | T-0310 | ST-0303 | E03 | Apply signing stack to exl-prod; CMK + buckets + roles live | AWS2 | S3 | 1 |  |  | T-0309,T-0304 |  | Planned
Task | T-0311 | ST-0303 | E03 | Run publish-key; PEM in public bucket | AWS2 | S3 | 0.5 |  |  | T-0310 |  | Planned
Task | T-0312 | ST-0303 | E03 | Cross-account verify test with real ABSA principal | AWS2 | S4 | 1 |  |  | T-0311 | ABSA: IAM ARNs | Planned
Story | ST-0304 | E03 | E03 | Registry API on real AWS |  | S3-S4 | 7 | 8 | Must |  |  |  | registry-api on Lambda+APIGW dev->prod; SigV4 register smoke passes.
Task | T-0313 | ST-0304 | E03 | Lambda packaging for registry-api (adapter + artifact build) | AWS2 | S3 | 2 |  |  | T-0304 |  | Planned | Largest demo->prod gap per Phase 3 closeout
Task | T-0314 | ST-0304 | E03 | Finish Lambda packaging + tests | AWS2 | S4 | 1 |  |  | T-0313 |  | Planned
Task | T-0315 | ST-0304 | E03 | Apply APIGW+Lambda+DynamoDB registry stack (dev) + smoke | AWS2 | S4 | 2 |  |  | T-0314 |  | Planned
Task | T-0316 | ST-0304 | E03 | SigV4 register smoke from pipeline-factory | TL | S4 | 1 |  |  | T-0315 |  | Planned
Task | T-0317 | ST-0304 | E03 | Promote registry to stg + prod | AWS2 | S4 | 1 |  |  | T-0316 |  | Planned
Story | ST-0305 | E03 | E03 | S3 replication path |  | S4 | 2.5 | 3 | Must |  |  |  | Replication modules applied; encrypted transfer validated with ABSA test object.
Task | T-0318 | ST-0305 | E03 | Apply s3-replication source + destination modules | AWS | S4 | 1.5 |  |  | T-0306 | ABSA: data movement | Planned
Task | T-0319 | ST-0305 | E03 | Encrypted transfer validated end-to-end with ABSA test object | AWS | S4 | 1 |  |  | T-0318 | ABSA: data movement | Planned
EPIC | E04 |  | E04 | Data Engineering & Quality - Data contracts, ingestion validation, DQ (volume+drift), reconciliation, lineage, retention, PIR. | DE | S1-S7
Story | ST-0401 | E04 | E04 | Data contracts per model |  | S1-S2 | 6 | 8 | Must |  |  |  | Data dictionary template + input schemas for models 1-2; volume/cadence matrix for all 10.
Task | T-0401 | ST-0401 | E04 | Study platform-contracts schemas + PIR mapping + demo data flow | DE | S1 | 1 |  |  |  |  | Planned
Task | T-0402 | ST-0401 | E04 | Data dictionary template (input schema, types, nullability, PIR link) | DE | S1 | 2 |  |  | T-0401 |  | Planned
Task | T-0403 | ST-0401 | E04 | Input schemas for models 1-2 | DE | S2 | 2 |  |  | T-0402 | ABSA: model docs | Planned
Task | T-0404 | ST-0401 | E04 | Volume/cadence matrix for all 10 models | DE | S2 | 1 |  |  | T-0402 |  | Planned | Daily / weekly / monthly per model
Story | ST-0402 | E04 | E04 | Ingestion & arrival validation |  | S2-S3 | 5 | 5 | Must |  |  |  | Bucket layout convention; schema-on-arrival validation; reject/return-to-ABSA workflow.
Task | T-0405 | ST-0402 | E04 | Bucket layout + partitioning convention for scoring inputs | DE | S2 | 1 |  |  | T-0402 |  | Planned
Task | T-0406 | ST-0402 | E04 | Arrival validation job: schema check on landing | DE | S3 | 3 |  |  | T-0405 |  | Planned
Task | T-0407 | ST-0402 | E04 | Reject / return-to-ABSA workflow for failed files | DE | S3 | 1 |  |  | T-0406 |  | Planned
Story | ST-0403 | E04 | E04 | Data quality framework |  | S4-S5 | 6 | 8 | Must |  |  |  | Volume band checks + PSI drift design (feeds D01); DQ report artifact per run.
Task | T-0408 | ST-0403 | E04 | Volume checks: row-count expectation bands per model | DE | S4 | 2 |  |  | T-0406 |  | Planned
Task | T-0409 | ST-0403 | E04 | Drift metric design (PSI per feature) -> D01 proposal to ABSA | DE | S4 | 2 |  |  | T-0406 |  | Planned | Feeds open decision D01
Task | T-0410 | ST-0403 | E04 | DQ report artifact published per scoring run | DE | S5 | 2 |  |  | T-0408 |  | Planned
Story | ST-0404 | E04 | E04 | PIR integration |  | S5-S6 | 4.5 | 5 | Must |  |  |  | pir.yaml synced from ABSA PIR system; coverage report on real model inputs.
Task | T-0411 | ST-0404 | E04 | PIR feed/API contract session with ABSA | DE | S5 | 0.5 |  |  |  | ABSA: PIR contract | Planned
Task | T-0412 | ST-0404 | E04 | pir.yaml sync from ABSA PIR system | DE | S5 | 3 |  |  | T-0411 | ABSA: PIR contract | Planned
Task | T-0413 | ST-0404 | E04 | PIR coverage report on real model inputs | DE | S6 | 1 |  |  | T-0412 |  | Planned
Story | ST-0405 | E04 | E04 | Group 1 data operations |  | S6-S7 | 4 | 5 | Must |  |  |  | Dress-rehearsal data prepared; DQ tuned on first production runs.
Task | T-0414 | ST-0405 | E04 | Dress-rehearsal data preparation (models 1-2) | DE | S6 | 2 |  |  | T-0403 |  | Planned
Task | T-0415 | ST-0405 | E04 | DQ on first production runs + threshold tuning | DE | S7 | 2 |  |  | T-0410 |  | Planned
Story | ST-0406 | E04 | E04 | Reconciliation & lineage |  | S3-S7 | 4 | 5 | Should |  |  |  | Source-vs-landing reconciliation; data lineage capture; backfill capability.
Task | T-0416 | ST-0406 | E04 | Source-vs-landing row-count reconciliation check | DE | S3 | 1 |  |  | T-0405 |  | Planned
Task | T-0417 | ST-0406 | E04 | Data lineage capture (input dataset -> run -> output) | DE | S6 | 1.5 |  |  | T-0406 |  | Planned
Task | T-0418 | ST-0406 | E04 | Backfill / re-run capability for missed cadence windows | DE | S7 | 1.5 |  |  | T-0406 |  | Planned
Story | ST-0407 | E04 | E04 | Retention implementation |  | S7 | 1 | 1 | Should |  |  |  | S3 retention/archival implemented and verified per model class.
Task | T-0419 | ST-0407 | E04 | Implement + verify S3 retention/archival per model class | DE | S7 | 1 |  |  | T-0703pol |  | Planned | Pairs with AWS T-0703
EPIC | E05 |  | E05 | SAS Model Engineering - Standards & Tooling - SAS prod-readiness standards, real SAS linting, reconciliation framework. | SAS | S1-S3
Story | ST-0501 | E05 | E05 | SAS standards & tooling |  | S1-S3 | 9 | 13 | Must |  |  |  | Prod-readiness standards published; SAS runtime obtained; static_sas upgraded to real lint.
Task | T-0501 | ST-0501 | E05 | Study credit-risk-pd package + static_sas checker internals | SAS | S1 | 2 |  |  |  |  | Planned
Task | T-0501b | ST-0501 | E05 | Study credit-risk-pd package + SAS standards (with SAS #1) | SAS2 | S1 | 1.5 |  |  |  |  | Planned
Task | T-0502 | ST-0501 | E05 | SAS prod-readiness standards doc (naming, macros, errors, logging) | SAS | S1 | 2 |  |  | T-0501 |  | Planned
Task | T-0503 | ST-0501 | E05 | Obtain SAS runtime image + license terms from ABSA | SAS2 | S2 | 0.5 |  |  |  | ABSA: SAS runtime | Planned
Task | T-0504 | ST-0501 | E05 | Upgrade static_sas checker from structural to real lint | SAS2 | S3 | 3 |  |  | T-0503 | ABSA: SAS runtime | Planned | Pairs with TL on checker plumbing
Story | ST-0504 | E05 | E05 | Reconciliation framework |  | S4-S6 | 3 | 3 | Must |  |  |  | Diff tool with tolerance bands + per-variable deltas; PIR-ready report template.
Task | T-0514 | ST-0504 | E05 | Output diff tool: tolerance bands, per-variable deltas | SAS | S4 | 2 |  |  | T-0508 |  | Planned | Co-design with DE
Task | T-0515 | ST-0504 | E05 | Reconciliation report template (PIR-ready) | SAS | S6 | 1 |  |  | T-0514 |  | Planned
EPIC | E06 |  | E06 | ML Compute & Pipeline Execution - Compute platform decision (D04), real Step Functions execution, schedules, prod promote. | AWS | S3-S6
Story | ST-0601 | E06 | E06 | Compute platform decision (D04) |  | S3 | 1 | 1 | Must |  |  |  | ADR records SFN+Lambda vs SageMaker choice with ABSA architecture board.
Task | T-0601 | ST-0601 | E06 | ADR: D04 compute choice (SFN+Lambda vs SageMaker) w/ architecture board | AWS2 | S3 | 1 |  |  |  |  | Planned | Gates compute build in S5
Story | ST-0602 | E06 | E06 | Step Functions runtime execution |  | S5-S6 | 8 | 8 | Must |  |  |  | Model-1 ASL executes on real AWS in dev; compute layer built; EventBridge schedules set.
Task | T-0602 | ST-0602 | E06 | Deploy real ASL standard-batch for model-1 (dev) | AWS2 | S5 | 3 |  |  | T-0601,T-0509 |  | Planned
Task | T-0603 | ST-0602 | E06 | Build compute layer - core (Lambda container / SM Processing per D04) | AWS2 | S5 | 2 |  |  | T-0601 |  | Planned
Task | T-0603b | ST-0602 | E06 | Build compute layer - finalize + integrate | AWS2 | S6 | 2 |  |  | T-0603 |  | Planned
Task | T-0604 | ST-0602 | E06 | EventBridge schedules per model cadence | AWS2 | S6 | 1 |  |  | T-0602 |  | Planned
Story | ST-0603 | E06 | E06 | Production pipeline infra |  | S6 | 3 | 3 | Must |  |  |  | Prod promote done; SLA bands defined.
Task | T-0605 | ST-0603 | E06 | Promote pipeline infra to prod | AWS2 | S6 | 2 |  |  | T-0602 |  | Planned
Task | T-0606 | ST-0603 | E06 | Define SLA bands per model cadence | AWS2 | S6 | 1 |  |  | T-0605 |  | Planned | Feeds perf test T-1202/1203
EPIC | E07 |  | E07 | Security, Controls & Compliance - Change workflow, threat model, IAM least-privilege, encryption validation, pen-test, POPIA/SARB, audit pack. | TL | S2-S8
Story | ST-0701 | E07 | E07 | Change workflow (D02) |  | S5 | 2 | 2 | Must |  |  |  | CAB/IVU mapped to registry approve route; production-change path documented.
Task | T-0701 | ST-0701 | E07 | Map CAB/IVU contract onto registry approve/retire routes (D02) | TL | S5 | 2 |  |  |  | ABSA: CAB/IVU contract | Planned
Story | ST-0702 | E07 | E07 | Rotation, retention policy & access audit |  | S4-S7 | 4 | 5 | Must |  |  |  | Rotation cadence doc; S3 lifecycle policies; KMS rotation drill; pre-go-live access audit.
Task | T-0702 | ST-0702 | E07 | Rotation cadence doc: Jenkins creds, bot PAT, registrar tokens (D03) | DevOps | S4 | 1 |  |  | T-0211 |  | Planned
Task | T-0703pol | ST-0702 | E07 | S3 lifecycle/retention policies authored per retention rules | AWS | S7 | 1 |  |  | T-0318 |  | Planned
Task | T-0704 | ST-0702 | E07 | KMS rotation drill per docs/runbooks/kms-key-rotation.md | DevOps | S7 | 1 |  |  | T-0311 |  | Planned | AWS supports 0.5d
Task | T-0705 | ST-0702 | E07 | Pre-go-live access review + least-privilege audit | AWS | S7 | 1 |  |  | T-0310 |  | Planned
Story | ST-0703 | E07 | E07 | Security assurance |  | S4-S8 | 7 | 8 | Must |  |  |  | Threat model, IAM least-privilege audit, encryption validation, pen-test + remediation.
Task | T-0706 | ST-0703 | E07 | Threat model workshop (STRIDE) on cross-account signing chain | TL | S4 | 1.5 |  |  |  |  | Planned | AWS co-runs
Task | T-0707 | ST-0703 | E07 | IAM least-privilege audit (automated policy analysis) | AWS2 | S7 | 1.5 |  |  | T-0310 |  | Planned
Task | T-0708 | ST-0703 | E07 | Encryption validation: in-transit (TLS/replication) + at-rest (KMS) evidence | AWS2 | S7 | 1.5 |  |  | T-0318 |  | Planned
Task | T-0709 | ST-0703 | E07 | Pen-test coordination + scope with ABSA security | DevOps | S7 | 1 |  |  |  |  | Planned
Task | T-0710 | ST-0703 | E07 | Pen-test remediation window | DevOps | S8 | 1.5 |  |  | T-0709 |  | Planned
Story | ST-0704 | E07 | E07 | Compliance evidence |  | S6-S8 | 3 | 3 | Must |  |  |  | POPIA/SARB control verification vs control-matrix; G1 audit evidence pack assembled.
Task | T-0711 | ST-0704 | E07 | POPIA/SARB control verification vs control-matrix | TL | S6 | 1.5 |  |  |  |  | Planned
Task | T-0712 | ST-0704 | E07 | Audit evidence pack assembly (G1) for ABSA risk + external audit | TL | S8 | 1.5 |  |  | T-0813 |  | Planned
EPIC | E08 |  | E08 | Group 1 - Model Onboarding (Models 1-2) - Models 1-2: review, optimize, package, reconcile vs ABSA benchmarks. The proof of the chain. | SAS | S2-S6
Story | ST-0502 | E08 | E08 | Model 1 onboarding (SAS #1) |  | S2-S4 | 10.5 | 13 | Must |  |  |  | Optimized code reconciles vs ABSA benchmarks; packaged per ADR-0010; code-intake green.
Task | T-0505 | ST-0502 | E08 | Model-1 dev-code review vs benchmark spec | SAS | S2 | 2 |  |  | T-0502 | ABSA: model docs | Planned
Task | T-0506 | ST-0502 | E08 | Benchmark spec gap notes; clarify with ABSA model owner | SAS | S2 | 1 |  |  | T-0505 |  | Planned
Task | T-0507 | ST-0502 | E08 | Optimize + standardize model-1 scoring code (profile, refactor, unit-test) | SAS | S3 | 4 |  |  | T-0505 |  | Planned
Task | T-0508 | ST-0502 | E08 | Regression harness vs ABSA benchmark outputs | SAS | S4 | 2 |  |  | T-0507 |  | Planned
Task | T-0509 | ST-0502 | E08 | Package model-1 per ADR-0010; code-intake validate green | SAS | S4 | 1 |  |  | T-0508 |  | Planned
Task | T-0516 | ST-0502 | E08 | Model-1 implementation doc: generate (IDG) + review + approve | SAS | S8 | 0.5 |  |  | T-1405 |  | Planned | ADR-0012; living doc per version
Story | ST-0503 | E08 | E08 | Model 2 onboarding (SAS #2, in parallel) |  | S2-S6 | 9.5 | 13 | Must |  |  |  | Same exit criteria as model 1; runs in parallel on the 2nd SAS dev to de-risk the proof.
Task | T-0510 | ST-0503 | E08 | Model-2 dev-code review vs benchmark spec | SAS2 | S3 | 2 |  |  | T-0502 | ABSA: model docs | Planned | Parallel to model-1 on SAS #1
Task | T-0511 | ST-0503 | E08 | Optimize + standardize model-2 scoring code (profile, refactor, unit-test) | SAS2 | S4 | 4 |  |  | T-0510 |  | Planned
Task | T-0512 | ST-0503 | E08 | Model-2 regression harness | SAS2 | S5 | 2 |  |  | T-0511 |  | Planned
Task | T-0513 | ST-0503 | E08 | Package model-2 + code-intake green | SAS2 | S5 | 1 |  |  | T-0512 |  | Planned
Task | T-0517 | ST-0503 | E08 | Model-2 implementation doc: generate (IDG) + review + approve | SAS2 | S8 | 0.5 |  |  | T-1405 |  | Planned | ADR-0012
EPIC | E09 |  | E09 | Observability, Dashboards & Delivery - Run-status dashboards, alerting, DQ/drift panels, cost dashboard, automated signed output delivery. | DevOps | S4-S9
Story | ST-0901 | E09 | E09 | Dashboard tooling & build |  | S4-S6 | 4.5 | 5 | Must |  |  |  | D08 decided; run-status dashboard live for G1 runs.
Task | T-0901 | ST-0901 | E09 | D08 tooling decision: CloudWatch / Grafana / QuickSight | DevOps | S4 | 1.5 |  |  |  |  | Planned
Task | T-0902 | ST-0901 | E09 | Run-status dashboard build (runs, exceptions, durations) | DevOps | S6 | 3 |  |  | T-0901 |  | Planned
Story | ST-0902 | E09 | E09 | Alerting & notifications |  | S5-S9 | 3 | 3 | Must |  |  |  | Failure alerts routed; ABSA SPOC notification path tested.
Task | T-0903 | ST-0902 | E09 | Alert routing: SNS -> email/Slack; severity mapping | DevOps | S5 | 2 |  |  | T-0901 |  | Planned
Task | T-0904 | ST-0902 | E09 | Failure notifications to ABSA SPOC path tested | DevOps | S9 | 1 |  |  | T-0903 |  | Planned
Story | ST-0903 | E09 | E09 | DQ / drift panels |  | S8 | 2 | 2 | Should |  |  |  | DQ + drift panels visible alongside run status.
Task | T-0905 | ST-0903 | E09 | DQ + drift panels alongside run status | DE | S8 | 2 |  |  | T-0410,T-0902 |  | Planned
Story | ST-0904 | E09 | E09 | Output delivery automation (D09) |  | S8-S9 | 4 | 5 | Must |  |  |  | Signed outputs auto-delivered to ABSA with confirmation evidence; validated with recipients.
Task | T-0906 | ST-0904 | E09 | Automated signed output delivery to ABSA + confirmation evidence | DevOps | S8 | 2 |  |  | T-0319 | ABSA: data movement | Planned
Task | T-0907 | ST-0904 | E09 | Delivery validation with ABSA recipients | DevOps | S9 | 1 |  |  | T-0906 |  | Planned
Task | T-0908 | ST-0904 | E09 | Dashboard access + validation with ABSA recipients | DevOps | S9 | 1 |  |  | T-0902 |  | Planned
Story | ST-0905 | E09 | E09 | Operational monitoring depth |  | S6-S9 | 2 | 2 | Should |  |  |  | Per-pipeline alarms baseline; cost & usage dashboard.
Task | T-0909 | ST-0905 | E09 | Per-pipeline CloudWatch alarms + dashboard baseline | DevOps | S6 | 1 |  |  | T-0901 |  | Planned
Task | T-0910 | ST-0905 | E09 | Cost & usage dashboard | DevOps | S9 | 1 |  |  | T-0901 |  | Planned
EPIC | E10 |  | E10 | Group 2 - Scale-Out (Models 3-10) - Template-driven onboarding across 3 SAS devs: 3 models/sprint in S9-S10, 2 in S11. ALL 10 models scoring by end S11; S12 is hardening + sign-off only (no new model onboarding). | SAS x3 | S8-S11
Story | ST-0801 | E10 | E10 | Dress rehearsal (full chain) |  | S6 | 7 | 8 | Must |  |  |  | Producer + verifier chain on real AWS for models 1-2; transcript archived; defects logged.
Task | T-0801 | ST-0801 | E10 | Dress rehearsal orchestration: full chain on real AWS, models 1-2 | TL | S6 | 2 |  |  | T-0513,T-0602,T-0317 |  | Planned | Producer + verifier, archived transcript
Task | T-0802 | ST-0801 | E10 | Dress rehearsal infra support + fixes | AWS | S6 | 2 |  |  | T-0801 |  | Planned
Task | T-0803 | ST-0801 | E10 | Dress rehearsal model runs + output checks | SAS | S6 | 2 |  |  | T-0801 |  | Planned
Task | T-0804 | ST-0801 | E10 | Dress rehearsal CI/pipeline ops | DevOps | S6 | 1 |  |  | T-0801 |  | Planned
Story | ST-0802 | E10 | E10 | Group 1 production scoring |  | S7 | 3 | 3 | Must |  |  |  | Initial scheduled runs in prod; outputs delivered; DQ green.
Task | T-0805 | ST-0802 | E10 | Initial production scoring runs (models 1-2) | AWS2 | S7 | 2 |  |  | T-0801 |  | Planned
Task | T-0806 | ST-0802 | E10 | Production run monitoring + incident handling | DevOps | S7 | 1 |  |  | T-0805 |  | Planned
Story | ST-0803 | E10 | E10 | Reconciliation & defect cycle |  | S7-S8 | 9 | 13 | Must |  |  |  | Outputs reconcile within tolerance; defects closed and re-run.
Task | T-0807 | ST-0803 | E10 | Reconcile G1 outputs vs benchmarks (tolerance report) | SAS | S7 | 3 |  |  | T-0805,T-0514 |  | Planned
Task | T-0808 | ST-0803 | E10 | Defect triage + fix cycle | SAS2 | S7 | 3 |  |  | T-0807 |  | Planned
Task | T-0809 | ST-0803 | E10 | Defect triage facilitation + ABSA comms | TL | S7 | 1 |  |  | T-0807 |  | Planned
Task | T-0810 | ST-0803 | E10 | Defect closure + re-run + final reconciliation | SAS | S8 | 2 |  |  | T-0808 |  | Planned
Story | ST-0804 | E10 | E10 | PIR & ABSA sign-off |  | S8 | 5.5 | 8 | Must |  |  |  | PIR evidence pack submitted; written ABSA Risk Owner sign-off (THE program gate).
Task | T-0811 | ST-0804 | E10 | PIR evidence pack (reconciliation, DQ, audit trail) | SAS | S8 | 2 |  |  | T-0810 |  | Planned
Task | T-0812 | ST-0804 | E10 | PIR data evidence: lineage + DQ reports | DE | S8 | 1 |  |  | T-0810 |  | Planned
Task | T-0813 | ST-0804 | E10 | ABSA sign-off review meeting + written sign-off | TL | S8 | 2 |  |  | T-0811 |  | Planned | *** THE program gate ***
Task | T-0814 | ST-0804 | E10 | G1 production schedules confirmed live | AWS2 | S8 | 0.5 |  |  | T-0813 |  | Planned
Story | ST-1001 | E10 | E10 | Group 2 onboarding plan |  | S8 | 1 | 1 | Must |  |  |  | Per-model checklist derived from G1 lessons; wave allocation agreed.
Task | T-1001 | ST-1001 | E10 | Group 2 onboarding plan + per-model checklist from G1 lessons | TL | S8 | 1 |  |  | T-0813 |  | Planned
Story | ST-1002 | E10 | E10 | Wave 1: models 3-5 (3 SAS devs) |  | S9 | 29 | 13 | Must |  |  |  | All three models scoring in prod, reconciled, PIR'd.
Task | T-M03-DC | ST-1002 | E10 | Model 3: contract + input schema | DE | S9 | 1 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M03-DQ | ST-1002 | E10 | Model 3: DQ rules + verification | DE | S9 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M03-RV | ST-1002 | E10 | Model 3: code review vs benchmark spec | SAS | S9 | 1 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M03-OPT | ST-1002 | E10 | Model 3: profile + optimize + unit-test scoring code | SAS | S9 | 2.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M03-PKG | ST-1002 | E10 | Model 3: package per ADR-0010 + code-intake green | SAS | S9 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M03-REC | ST-1002 | E10 | Model 3: reconcile vs benchmark + defect fix | SAS | S9 | 1.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M03-PIR | ST-1002 | E10 | Model 3: PIR pack + sign-off prep | SAS | S9 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M03-IDD | ST-1002 | E10 | Model 3: implementation doc: generate (IDG) + approve | SAS | S9 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M03-PIPE | ST-1002 | E10 | Model 3: pipeline config + EventBridge schedule | AWS | S9 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M03-DEP | ST-1002 | E10 | Model 3: deploy to prod + smoke | AWS | S9 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M03-MON | ST-1002 | E10 | Model 3: CI + monitoring wiring | DevOps | S9 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M04-DC | ST-1002 | E10 | Model 4: contract + input schema | DE | S9 | 1 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M04-DQ | ST-1002 | E10 | Model 4: DQ rules + verification | DE | S9 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M04-RV | ST-1002 | E10 | Model 4: code review vs benchmark spec | SAS2 | S9 | 1 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M04-OPT | ST-1002 | E10 | Model 4: profile + optimize + unit-test scoring code | SAS2 | S9 | 2.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M04-PKG | ST-1002 | E10 | Model 4: package per ADR-0010 + code-intake green | SAS2 | S9 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M04-REC | ST-1002 | E10 | Model 4: reconcile vs benchmark + defect fix | SAS2 | S9 | 1.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M04-PIR | ST-1002 | E10 | Model 4: PIR pack + sign-off prep | SAS2 | S9 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M04-IDD | ST-1002 | E10 | Model 4: implementation doc: generate (IDG) + approve | SAS2 | S9 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M04-PIPE | ST-1002 | E10 | Model 4: pipeline config + EventBridge schedule | AWS | S9 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M04-DEP | ST-1002 | E10 | Model 4: deploy to prod + smoke | AWS | S9 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M04-MON | ST-1002 | E10 | Model 4: CI + monitoring wiring | DevOps | S9 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M05-DC | ST-1002 | E10 | Model 5: contract + input schema | DE | S9 | 1 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS3
Task | T-M05-DQ | ST-1002 | E10 | Model 5: DQ rules + verification | DE | S9 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS3
Task | T-M05-RV | ST-1002 | E10 | Model 5: code review vs benchmark spec | SAS3 | S9 | 1 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS3
Task | T-M05-OPT | ST-1002 | E10 | Model 5: profile + optimize + unit-test scoring code | SAS3 | S9 | 2.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS3
Task | T-M05-PKG | ST-1002 | E10 | Model 5: package per ADR-0010 + code-intake green | SAS3 | S9 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS3
Task | T-M05-REC | ST-1002 | E10 | Model 5: reconcile vs benchmark + defect fix | SAS3 | S9 | 1.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS3
Task | T-M05-PIR | ST-1002 | E10 | Model 5: PIR pack + sign-off prep | SAS3 | S9 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS3
Task | T-M05-IDD | ST-1002 | E10 | Model 5: implementation doc: generate (IDG) + approve | SAS3 | S9 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS3
Task | T-M05-PIPE | ST-1002 | E10 | Model 5: pipeline config + EventBridge schedule | AWS | S9 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS3
Task | T-M05-DEP | ST-1002 | E10 | Model 5: deploy to prod + smoke | AWS | S9 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS3
Task | T-M05-MON | ST-1002 | E10 | Model 5: CI + monitoring wiring | DevOps | S9 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS3
Task | T-W9 | ST-1002 | E10 | Wave review + ABSA checkpoint (S9) | TL | S9 | 0.5 |  |  |  |  | Planned
Story | ST-1003 | E10 | E10 | Wave 2: models 6-8 (3 SAS devs) |  | S10 | 29 | 13 | Must |  |  |  | Same exit criteria.
Task | T-M06-DC | ST-1003 | E10 | Model 6: contract + input schema | DE | S10 | 1 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M06-DQ | ST-1003 | E10 | Model 6: DQ rules + verification | DE | S10 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M06-RV | ST-1003 | E10 | Model 6: code review vs benchmark spec | SAS | S10 | 1 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M06-OPT | ST-1003 | E10 | Model 6: profile + optimize + unit-test scoring code | SAS | S10 | 2.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M06-PKG | ST-1003 | E10 | Model 6: package per ADR-0010 + code-intake green | SAS | S10 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M06-REC | ST-1003 | E10 | Model 6: reconcile vs benchmark + defect fix | SAS | S10 | 1.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M06-PIR | ST-1003 | E10 | Model 6: PIR pack + sign-off prep | SAS | S10 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M06-IDD | ST-1003 | E10 | Model 6: implementation doc: generate (IDG) + approve | SAS | S10 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M06-PIPE | ST-1003 | E10 | Model 6: pipeline config + EventBridge schedule | AWS | S10 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M06-DEP | ST-1003 | E10 | Model 6: deploy to prod + smoke | AWS | S10 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M06-MON | ST-1003 | E10 | Model 6: CI + monitoring wiring | DevOps | S10 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M07-DC | ST-1003 | E10 | Model 7: contract + input schema | DE | S10 | 1 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M07-DQ | ST-1003 | E10 | Model 7: DQ rules + verification | DE | S10 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M07-RV | ST-1003 | E10 | Model 7: code review vs benchmark spec | SAS2 | S10 | 1 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M07-OPT | ST-1003 | E10 | Model 7: profile + optimize + unit-test scoring code | SAS2 | S10 | 2.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M07-PKG | ST-1003 | E10 | Model 7: package per ADR-0010 + code-intake green | SAS2 | S10 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M07-REC | ST-1003 | E10 | Model 7: reconcile vs benchmark + defect fix | SAS2 | S10 | 1.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M07-PIR | ST-1003 | E10 | Model 7: PIR pack + sign-off prep | SAS2 | S10 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M07-IDD | ST-1003 | E10 | Model 7: implementation doc: generate (IDG) + approve | SAS2 | S10 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M07-PIPE | ST-1003 | E10 | Model 7: pipeline config + EventBridge schedule | AWS | S10 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M07-DEP | ST-1003 | E10 | Model 7: deploy to prod + smoke | AWS | S10 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M07-MON | ST-1003 | E10 | Model 7: CI + monitoring wiring | DevOps | S10 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M08-DC | ST-1003 | E10 | Model 8: contract + input schema | DE | S10 | 1 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS3
Task | T-M08-DQ | ST-1003 | E10 | Model 8: DQ rules + verification | DE | S10 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS3
Task | T-M08-RV | ST-1003 | E10 | Model 8: code review vs benchmark spec | SAS3 | S10 | 1 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS3
Task | T-M08-OPT | ST-1003 | E10 | Model 8: profile + optimize + unit-test scoring code | SAS3 | S10 | 2.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS3
Task | T-M08-PKG | ST-1003 | E10 | Model 8: package per ADR-0010 + code-intake green | SAS3 | S10 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS3
Task | T-M08-REC | ST-1003 | E10 | Model 8: reconcile vs benchmark + defect fix | SAS3 | S10 | 1.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS3
Task | T-M08-PIR | ST-1003 | E10 | Model 8: PIR pack + sign-off prep | SAS3 | S10 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS3
Task | T-M08-IDD | ST-1003 | E10 | Model 8: implementation doc: generate (IDG) + approve | SAS3 | S10 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS3
Task | T-M08-PIPE | ST-1003 | E10 | Model 8: pipeline config + EventBridge schedule | AWS | S10 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS3
Task | T-M08-DEP | ST-1003 | E10 | Model 8: deploy to prod + smoke | AWS | S10 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS3
Task | T-M08-MON | ST-1003 | E10 | Model 8: CI + monitoring wiring | DevOps | S10 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS3
Task | T-W10 | ST-1003 | E10 | Wave review + ABSA checkpoint (S10) | TL | S10 | 0.5 |  |  |  |  | Planned
Story | ST-1004 | E10 | E10 | Wave 3: models 9-10 - ALL 10 LIVE |  | S11 | 23.5 | 13 | Must |  |  |  | Final 2 models scoring; all 10 models live by end S11; 3rd SAS dev floats on reconciliation/defects.
Task | T-M09-DC | ST-1004 | E10 | Model 9: contract + input schema | DE | S11 | 1 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M09-DQ | ST-1004 | E10 | Model 9: DQ rules + verification | DE | S11 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M09-RV | ST-1004 | E10 | Model 9: code review vs benchmark spec | SAS | S11 | 1 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M09-OPT | ST-1004 | E10 | Model 9: profile + optimize + unit-test scoring code | SAS | S11 | 2.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M09-PKG | ST-1004 | E10 | Model 9: package per ADR-0010 + code-intake green | SAS | S11 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M09-REC | ST-1004 | E10 | Model 9: reconcile vs benchmark + defect fix | SAS | S11 | 1.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M09-PIR | ST-1004 | E10 | Model 9: PIR pack + sign-off prep | SAS | S11 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M09-IDD | ST-1004 | E10 | Model 9: implementation doc: generate (IDG) + approve | SAS | S11 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M09-PIPE | ST-1004 | E10 | Model 9: pipeline config + EventBridge schedule | AWS | S11 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M09-DEP | ST-1004 | E10 | Model 9: deploy to prod + smoke | AWS | S11 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M09-MON | ST-1004 | E10 | Model 9: CI + monitoring wiring | DevOps | S11 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS
Task | T-M10-DC | ST-1004 | E10 | Model 10: contract + input schema | DE | S11 | 1 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M10-DQ | ST-1004 | E10 | Model 10: DQ rules + verification | DE | S11 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M10-RV | ST-1004 | E10 | Model 10: code review vs benchmark spec | SAS2 | S11 | 1 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M10-OPT | ST-1004 | E10 | Model 10: profile + optimize + unit-test scoring code | SAS2 | S11 | 2.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M10-PKG | ST-1004 | E10 | Model 10: package per ADR-0010 + code-intake green | SAS2 | S11 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M10-REC | ST-1004 | E10 | Model 10: reconcile vs benchmark + defect fix | SAS2 | S11 | 1.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M10-PIR | ST-1004 | E10 | Model 10: PIR pack + sign-off prep | SAS2 | S11 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M10-IDD | ST-1004 | E10 | Model 10: implementation doc: generate (IDG) + approve | SAS2 | S11 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M10-PIPE | ST-1004 | E10 | Model 10: pipeline config + EventBridge schedule | AWS | S11 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M10-DEP | ST-1004 | E10 | Model 10: deploy to prod + smoke | AWS | S11 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M10-MON | ST-1004 | E10 | Model 10: CI + monitoring wiring | DevOps | S11 | 0.5 |  |  | T-1001 |  | Planned | Group 2; SAS owner SAS2
Task | T-M-FLOAT | ST-1004 | E10 | Reconciliation depth + defect sweep across wave 3 | SAS3 | S11 | 4 |  |  | T-M09-OPT,T-M10-OPT |  | Planned | Spare SAS capacity = defect buffer
Task | T-W11 | ST-1004 | E10 | Wave review + ABSA checkpoint (S11) | TL | S11 | 0.5 |  |  |  |  | Planned
Story | ST-1005 | E10 | E10 | S12 hardening + Group 2 sign-off |  | S12 | 11.5 | 13 | Must |  |  |  | No new models. Final reconciliation sweep, defect closure, KT; written Group 2 sign-off.
Task | T-1025 | ST-1005 | E10 | Group 2 sign-off pack + ABSA meeting | TL | S12 | 2 |  |  |  |  | Planned | Closes initial onboarding scope
Task | T-1501 | ST-1005 | E10 | Final cross-model reconciliation sweep + tolerance sign-off | SAS | S12 | 3 |  |  |  |  | Planned
Task | T-1502 | ST-1005 | E10 | Group 2 defect closure + re-run verification | SAS2 | S12 | 3 |  |  |  |  | Planned
Task | T-1503 | ST-1005 | E10 | Group 2 knowledge transfer + per-model runbooks | SAS3 | S12 | 2 |  |  |  |  | Planned
Task | T-1504 | ST-1005 | E10 | Group 2 DQ + lineage evidence pack | DE | S12 | 1.5 |  |  |  |  | Planned
EPIC | E11 |  | E11 | Steady State, Hypercare & Handover - Production readiness, cutover rehearsal, runbooks, DR, hypercare, service review, handover, go-live. | TL | S8-S12
Story | ST-1101 | E11 | E11 | Runbooks & support model |  | S11 | 6 | 8 | Must |  |  |  | Incident/recovery/rollback runbooks; support rota + escalation matrix.
Task | T-1101 | ST-1101 | E11 | Runbooks: incident, recovery, rollback per model family | DevOps | S11 | 3 |  |  | T-0806 |  | Planned
Task | T-1102 | ST-1101 | E11 | Support rota + escalation matrix | TL | S11 | 1 |  |  | T-1101 |  | Planned
Task | T-1103 | ST-1101 | E11 | Cost review + right-sizing pass | AWS2 | S11 | 2 |  |  | T-0814 |  | Planned
Story | ST-1102 | E11 | E11 | Handover & go-live |  | S12 | 5 | 5 | Must |  |  |  | Handover sessions done; service review cadence scheduled; steady-state checklist complete.
Task | T-1104 | ST-1102 | E11 | Quarterly service review template + first review scheduled | TL | S11 | 1 |  |  | T-1102 |  | Planned
Task | T-1105 | ST-1102 | E11 | Handover sessions: ops team + ABSA | TL | S12 | 2 |  |  | T-1101 |  | Planned
Task | T-1106 | ST-1102 | E11 | Handover support + docs finalization | DevOps | S12 | 1 |  |  | T-1105 |  | Planned
Task | T-1107 | ST-1102 | E11 | Steady-state go-live checklist + cutover | TL | S12 | 1 |  |  | T-1105 |  | Planned | Go-live ~Dec 1, 2026
Story | ST-1103 | E11 | E11 | Production readiness & hypercare |  | S8-S12 | 4.5 | 5 | Must |  |  |  | Go/no-go review; cutover rehearsal; DR verified; hypercare defined; ops handbook.
Task | T-1108 | ST-1103 | E11 | G1 production readiness review (go/no-go checklist) | DevOps | S8 | 0.5 |  |  | T-0810 |  | Planned
Task | T-1109 | ST-1103 | E11 | Cutover rehearsal (G1) | DevOps | S8 | 1 |  |  | T-1108 |  | Planned
Task | T-1110 | ST-1103 | E11 | DR plan + backup/restore verification | AWS2 | S11 | 1.5 |  |  | T-0814 |  | Planned
Task | T-1111 | ST-1103 | E11 | Define hypercare period + staffing | TL | S12 | 0.5 |  |  | T-1107 |  | Planned
Task | T-1112 | ST-1103 | E11 | Ops handbook / knowledge base | DevOps | S12 | 1 |  |  | T-1101 |  | Planned
EPIC | E12 |  | E12 | Testing, UAT & Performance - Integration tests on real AWS, performance/load vs SLA, failure-mode/resilience, UAT with ABSA, regression pack. | TL | S5-S8
Story | ST-1201 | E12 | E12 | Integration & E2E testing |  | S5-S7 | 5.5 | 8 | Must |  |  |  | Integration suite on real AWS; perf/load test harness + execution vs SLA; resilience test.
Task | T-1201 | ST-1201 | E12 | Integration test suite on real AWS (beyond LocalStack) | TL | S5 | 1.5 |  |  | T-0317 |  | Planned
Task | T-1202 | ST-1201 | E12 | Performance/load test harness | DevOps | S6 | 1.5 |  |  | T-0605 |  | Planned
Task | T-1203 | ST-1201 | E12 | Performance test execution vs SLA bands | DevOps | S7 | 1.5 |  |  | T-1202,T-0606 |  | Planned
Task | T-1204 | ST-1201 | E12 | Failure-mode / resilience test (retry, partial failure, teardown) | DevOps | S7 | 1 |  |  | T-0805 |  | Planned
Story | ST-1202 | E12 | E12 | UAT with ABSA |  | S7-S8 | 3.5 | 5 | Must |  |  |  | UAT plan + scripts; UAT executed with ABSA on Group 1; sign-off captured.
Task | T-1205 | ST-1202 | E12 | UAT plan + scripts with ABSA | TL | S7 | 1.5 |  |  |  |  | Planned
Task | T-1206 | ST-1202 | E12 | UAT execution support (G1) with ABSA | DE | S8 | 1.5 |  |  | T-1205 |  | Planned
Task | T-1207 | ST-1202 | E12 | UAT sign-off capture | TL | S8 | 0.5 |  |  | T-1206 |  | Planned
Story | ST-1203 | E12 | E12 | Regression test pack |  | S8 | 1 | 1 | Should |  |  |  | Regression pack for ongoing changes wired into CI.
Task | T-1208 | ST-1203 | E12 | Regression test pack for ongoing changes | DevOps | S8 | 1 |  |  | T-0214 |  | Planned
EPIC | E13 |  | E13 | Capacity & Resourcing - 2-month capacity review; confirm 3rd SAS dev onboarding (S8) + AWS ramp-down plan after foundation (S7). | TL | S5-S8
Story | ST-1301 | E13 | E13 | Capacity review & AWS ramp-down |  | S5-S8 | 1.5 | 2 | Must |  |  |  | 2-month velocity review; confirm 3rd SAS dev onboarding (S8); plan AWS ramp-down/redeploy after S7 foundation.
Task | T-1301 | ST-1301 | E13 | 2-month capacity & velocity review; confirm 3rd SAS dev + AWS ramp-down plan | TL | S5 | 0.5 |  |  |  |  | Planned | *** S5 CAPACITY REVIEW ***
Task | T-1302 | ST-1301 | E13 | Initiate 3rd SAS dev sourcing/transfer; plan AWS redeploy after S7 | TL | S6 | 0.5 |  |  | T-1301 |  | Planned
Task | T-1303 | ST-1301 | E13 | Onboard 3rd SAS dev: access + repo + walkthrough | TL | S8 | 0.5 |  |  | T-1302 |  | Planned
Story | ST-1302 | E13 | E13 | 3rd SAS developer onboarding |  | S8 | 3 | 3 | Must |  |  |  | SAS3 productive: env green, standards studied, G1 reconciliation shadowed.
Task | T-1304 | ST-1302 | E13 | Clone repo, uv sync, tests green | SAS3 | S8 | 0.5 |  |  | T-1303 |  | Planned
Task | T-1305 | ST-1302 | E13 | Run `make demo` green locally | SAS3 | S8 | 0.5 |  |  | T-1304 |  | Planned
Task | T-1306 | ST-1302 | E13 | Study SAS standards + a packaged G1 model | SAS3 | S8 | 1 |  |  | T-1304 |  | Planned
Task | T-1307 | ST-1302 | E13 | Shadow a G1 reconciliation cycle | SAS3 | S8 | 1 |  |  | T-0810 |  | Planned
EPIC | E14 |  | E14 | Model Implementation Documentation (IDG) - LLM-assisted Implementation Document Generator (ADR-0012): drafts the per-version 'as-built' doc from dev docs + code + platform facts; human-approved; SR 11-7/GMRMG evidence; one living doc per model version. | TL | S5-S12
Story | ST-1401 | E14 | E14 | IDG design + decision |  | S5-S6 | 2 | 2 | Must |  |  |  | ADR-0012 accepted; impl-doc template + section schema; deterministic context-bundle spec; LLM provider DPA confirmed.
Task | T-1407 | ST-1401 | E14 | ADR-0012 + confirm LLM provider DPA (Azure OpenAI / Anthropic) with ABSA | TL | S5 | 0.5 |  |  |  | ABSA: LLM data-processing terms | Planned | *** gates first real IDG run ***
Task | T-1401 | ST-1401 | E14 | Design impl-doc template + section schema + deterministic context-bundle spec | TL | S6 | 1.5 |  |  | T-1407 |  | Planned | Co-design with SAS
Story | ST-1402 | E14 | E14 | IDG build |  | S7 | 5 | 5 | Must |  |  |  | Context bundler (facts from manifest/registry/validation) + LLM provider adapter (Azure OpenAI / Anthropic) + grounded prompt + raw-data/PII guard.
Task | T-1402 | ST-1402 | E14 | Build context bundler (facts from manifest/registry/validation summary) | AWS2 | S7 | 2 |  |  | T-1401,T-0317 |  | Planned | Facts injected verbatim, never LLM-authored
Task | T-1403 | ST-1402 | E14 | LLM provider adapter (Azure OpenAI / Anthropic) + grounded prompt | TL | S7 | 2 |  |  | T-1401 | ABSA: LLM data-processing terms | Planned | Provider-swappable behind an adapter
Task | T-1404 | ST-1402 | E14 | Raw-data / PII guard on the context bundle (pre-flight checker) | DE | S7 | 1 |  |  | T-1402 |  | Planned | Bundle = code+docs+metadata only; fail on data payload
Story | ST-1403 | E14 | E14 | IDG governance + integration |  | S7-S8 | 3.5 | 5 | Must |  |  |  | Render md+PDF; human review + approval workflow + provenance capture; implementation_doc_ref wired into package manifest + registry; G1 docs generated.
Task | T-1405 | ST-1403 | E14 | Render md + PDF; human review + approval workflow + provenance capture | AWS2 | S8 | 2 |  |  | T-1403 |  | Planned
Task | T-1406 | ST-1403 | E14 | Wire implementation_doc_ref into package-manifest + registry schema (regen models) | DE | S8 | 1.5 |  |  | T-1404 |  | Planned | Digest-reference pattern like python_pyproject_ref

## Sprint Plan
Sprint Plan - 12 x 2-week sprints
Sprint | Start | End | Goal | Milestone | AWS (d) | AWS2 (d) | DE (d) | SAS (d) | SAS2 (d) | SAS3 (d) | DevOps (d) | TL (d) | Total (d)
S1 | 2026-06-15 | 2026-06-26 | Team onboarded; Jenkins identity decided; python-validate green on Jenkins; ABSA ask-list sent
S2 | 2026-06-29 | 2026-07-10 | All no-AWS Jenkins jobs live; AWS bootstrap applied; data contracts started; SAS model-1 review done
S3 | 2026-07-13 | 2026-07-24 | Jenkins cutover complete (GHA retired); signing foundation live on real AWS; model-1 optimized | Jenkins is the sole CI gate
S4 | 2026-07-27 | 2026-08-07 | Registry API live on Lambda (dev); replication path validated; model-1 packaged; threat model done | Registry live in dev
S5 | 2026-08-10 | 2026-08-21 | SFN executes model-1 in dev; PIR sync; model-2 optimized; CAPACITY REVIEW (scale-up decision) | *** S5 CAPACITY REVIEW ***
S6 | 2026-08-24 | 2026-09-04 | DRESS REHEARSAL: full chain on real AWS for models 1-2; dashboards + perf harness; POPIA/SARB check | Dress rehearsal pass
S7 | 2026-09-07 | 2026-09-18 | Group 1 initial production scoring; reconciliation; perf + resilience tests; UAT plan
S8 | 2026-09-21 | 2026-10-02 | GROUP 1 ABSA SIGN-OFF; pen-test remediation; 2nd SAS dev onboarded; G2 plan | *** GROUP 1 SIGN-OFF ***
S9 | 2026-10-05 | 2026-10-16 | Group 2 wave 1 (models 3-5) live; dashboards validated with ABSA; cost dashboard
S10 | 2026-10-19 | 2026-10-30 | Group 2 wave 2 (models 6-8) live; output delivery automated
S11 | 2026-11-02 | 2026-11-13 | Group 2 wave 3 (models 9-10) live - ALL 10 MODELS SCORING; runbooks; DR verified | All 10 models live
S12 | 2026-11-16 | 2026-11-27 | HARDENING ONLY (no new models): GROUP 2 SIGN-OFF; handover; hypercare; steady-state go-live | *** GROUP 2 SIGN-OFF + GO-LIVE ***

## Role Load
Role Load vs Capacity (effort-days per sprint)
Role | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12
AWS - AWS/MLOps Eng #1 - Foundation & Infra
AWS2 - AWS/MLOps Eng #2 - Platform, Compute & MLOps
DE - Data Engineer
SAS - SAS Developer #1 (Model 1 / Group 2)
SAS2 - SAS Developer #2 (Model 2 / Group 2)
SAS3 - SAS Developer #3 (Group 2, from S8)
DevOps - DevOps Engineer
TL - Tech Lead (Vishnu)
Capacity (cap) | 8 / TL 6 | 8 / TL 6 | 8 / TL 6 | 8 / TL 6 | 8 / TL 6 | 8 / TL 6 | 8 / TL 6 | 8 / TL 6 | 8 / TL 6 | 8 / TL 6 | 8 / TL 6 | 8 / TL 6
Green = loaded within capacity ¦ Yellow = near cap (<=1d slack) ¦ Red = over capacity (re-plan) ¦ Grey = off-team (SAS3 before S8) ¦ Light = idle. Fills reflect the committed plan; values recalc live via SUMIFS. AWS2 idle late = redeploy lever (see README).

## Per-Model Tracker
Per-Model Onboarding Tracker (10 models)
Model | Group / Wave | Sprint(s) | SAS Owner | Cadence | Contract | Review | Optimize | Package | Deploy | Reconcile | Impl doc | PIR | Sign-off
Model 1 | Group 1 | S2-S8 | SAS | TBD (ABSA) | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned
Model 2 | Group 1 | S2-S8 | SAS2 | TBD (ABSA) | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned
Model 3 | Group 2 W1 | S9 | SAS | TBD | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned
Model 4 | Group 2 W1 | S9 | SAS2 | TBD | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned
Model 5 | Group 2 W1 | S9 | SAS3 | TBD | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned
Model 6 | Group 2 W2 | S10 | SAS | TBD | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned
Model 7 | Group 2 W2 | S10 | SAS2 | TBD | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned
Model 8 | Group 2 W2 | S10 | SAS3 | TBD | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned
Model 9 | Group 2 W3 | S11 | SAS | TBD | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned
Model 10 | Group 2 W3 | S11 | SAS2 | TBD | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned
Stages map to backlog tasks. Group 1 (models 1-2) is the proof; Group 2 (3-10) uses the template, 2 models/sprint split across SAS + SAS2. Update each stage cell to Done/WIP/Blocked.

## Governance & Cadence
Governance & Cadence
Ceremonies
Ceremony | When | Who | Outcome
Daily standup | Every working day, 15 min | All | Blockers surfaced same-day
Sprint planning | 1st Monday of each sprint, 2h | All | Sprint backlog committed
Backlog refinement | Mid-sprint Wednesday, 1h | TL + leads | Next sprint stories Ready
Sprint review + demo | 2nd Friday, 1h | All + ABSA optional | Working increment shown
Retrospective | 2nd Friday, 45 min | All | Actions logged + owned
Decision & Sign-off Checkpoints
Checkpoint | Sprint | Target date | Owner | Gate criteria
Kickoff + SPOCs confirmed | S1 | 2026-06-26 | TL | Charter + SPOCs signed
Jenkins cutover (GHA retired) | S3 | 2026-07-24 | DevOps | Jenkins sole CI gate; branch protection flipped
Registry live in dev | S4 | 2026-08-07 | AWS | SigV4 register smoke green
S5 CAPACITY REVIEW (confirm 3rd SAS + AWS ramp-down) | S5 | 2026-08-21 | TL | Confirm SAS3 onboarding S8; plan AWS redeploy after S7
Dress rehearsal pass | S6 | 2026-09-04 | TL | Full chain on real AWS, models 1-2
G1 production readiness (go/no-go) | S8 | 2026-10-02 | DevOps | Readiness checklist + cutover rehearsal clean
GROUP 1 ABSA SIGN-OFF | S8 | 2026-10-02 | ABSA Risk | Written sign-off; PIR + audit pack accepted
Steering checkpoint (mid-program) | S6 | 2026-09-04 | TL | Status + risk review with ABSA + EXL sponsors
ALL 10 MODELS LIVE (Group 2 onboarding complete) | S11 | 2026-11-13 | TL | Models 3-10 scoring; S12 reserved for hardening
Steering checkpoint (pre-go-live) | S11 | 2026-11-13 | TL | Go-live readiness review
GROUP 2 SIGN-OFF + go-live | S12 | 2026-11-27 | ABSA Risk | All 10 models signed off; steady-state begins

## RAID Log
RAID Log - Risks / Assumptions / Issues / Dependencies
Type | ID | Item | Owner | Sprint / Prob-Impact | Status / Mitigation
Dependency | DEP-01 | AWS account IDs (3 EXL + ABSA receiving) | ABSA | T-0304 (S2) | Open - bootstrap blocked; slips downstream day-for-day
Dependency | DEP-02 | IAM principal ARNs (kms:Verify / s3:GetObject) | ABSA | T-0312 (S4) | Open - cross-account verify untestable
Dependency | DEP-03 | SAS runtime Docker image + license | ABSA | T-0503/0504 (S2-S3) | Open - SAS validation stays structural-only
Dependency | DEP-04 | PIR system API/feed contract | ABSA | T-0411 (S5) | Open - pir.yaml hand-maintained
Dependency | DEP-05 | Data movement decision (S3 replication vs SFTP) | ABSA | T-0318/0906 (S4/S8) | Open - transfer + delivery blocked
Dependency | DEP-06 | CAB / IVU API contract | ABSA | T-0701 (S5) | Open - change workflow manual
Dependency | DEP-07 | Network connectivity choice (peering/TGW/PrivateLink) | ABSA | T-0307 (S3) | Open - data plane blocked
Dependency | DEP-08 | Approved model docs + code + benchmarks (1-2 first) | ABSA | T-0403/0505 (S2) | Open - SAS + DE model work blocked
Dependency | DEP-09 | LLM data-processing terms (Azure OpenAI / Anthropic): no-retention DPA + region | ABSA | T-1407/1403 (S5/S7) | Open - gates first real IDG run (ADR-0012); manual impl-doc fallback otherwise
Risk | RISK-01 | ABSA account onboarding delayed past S2 | TL | High / Med | 2 AWS engineers + ~2d/sprint slack in S2-S5 absorb a slip; pre-stage TF + tfvars; LocalStack keeps CI green; escalate end S1
Risk | RISK-02 | Group 1 sign-off (S8) slips, cascades to Group 2 | ABSA Risk | Med / High | Models 1-2 run in PARALLEL (2 SAS) from S2; dress rehearsal S6; defect buffer S7-S8
Risk | RISK-03 | Compute platform choice (D04) blocks S5 build | TL | Med / Med | Decision required end S3 at architecture board; AWS2 owns it
Risk | RISK-04 | Benchmark reconciliation discrepancies force rewrite | SAS | Med / High | Incremental validation; per-variable delta report; tolerance bands agreed early; S11 float + S12 hardening absorb rework
Risk | RISK-05 | 3rd SAS dev not sourced in time for S8 onboarding | TL | Med / Med | Start sourcing S6; 2 SAS from S1 already cover Group 2 at ~2 models/sprint as fallback (S9-S12)
Risk | RISK-06 | Signature byte-equivalence fails GHA vs Jenkins | DevOps | Low / High | S3 parallel-run week compares digests before cutover
Risk | RISK-07 | DevOps single-person peaks (S2 7.0, S6 6.5) - no DevOps redundancy | TL | Med / Med | TL pairs on Jenkins/dashboards at peaks; only un-doubled role - watch at S2/S6
Assumption | ASM-01 | 9-person team funded from S1 (3 AWS, 3 SAS [1 from S8], DE, DevOps, TL) | TL | All | Max-coverage shape chosen to make 12 sprints solid with absorption buffer
Assumption | ASM-02 | AWS2 redeploys or ramps down after S7 once foundation is built | TL | S8+ | Foundation is front-loaded; AWS load drops sharply S8-S12. 3rd AWS dropped (was under-utilized) - 2 carry the ~62-day AWS workload
Assumption | ASM-03 | All 10 models fit standard-batch / scalable-batch templates | TL | S6+ | Realtime tier is a placeholder; a realtime model would add scope
Assumption | ASM-04 | ABSA benchmarks are deterministic + reproducible | SAS | S4+ | Required for tolerance-band reconciliation to be meaningful
Assumption | ASM-05 | IDG sends the LLM code + docs + metadata ONLY - never raw data / PII | TL | S7+ | ADR-0012 data-minimisation guard; keeps IDG consistent with the data-residency posture (ADR-0001)
Issue | ISS-00 | (none logged yet - populate during delivery) | TL | - | -
Internal prerequisites (Sprint 0 / Sprint 1)
ID | Item | Owner | When
PRE-01 | Jira/ADO project + board created | TL | Before S1 planning
PRE-02 | GitHub repo write access for all engineers + CODEOWNERS updated | TL | Before S1 day 1
PRE-03 | Jenkins admin access for DevOps engineer | DevOps | Before S1 day 1
PRE-04 | AWS sandbox account access for AWS engineer | AWS | Before S1 day 1
PRE-05 | Dev machines: uv, Docker Desktop, Terraform 1.9.5, Python 3.12 | All | S1 day 1-2
PRE-06 | Slack/Teams channel + ceremony invites | TL | Before S1 planning
PRE-07 | SAS desktop/dev license (interim until ABSA runtime) | SAS | S1

## Dashboard
Delivery Dashboard
Tasks by Status |  |  | Effort by Role (d)
Status | Count |  | Role | Days
Planned |  |  | AWS
In Progress |  |  | AWS2
Done |  |  | DE
Blocked |  |  | SAS
SAS2
SAS3
DevOps
TL
Tasks + Effort by Epic
Epic | Title | Tasks | Effort (d) | Done
E01 | Team Onboarding & Governance
E02 | CI/CD on Existing Jenkins
E03 | AWS Foundation (Real Accounts)
E04 | Data Engineering & Quality
E05 | SAS Model Engineering - Standards & Tooling
E06 | ML Compute & Pipeline Execution
E07 | Security, Controls & Compliance
E08 | Group 1 - Model Onboarding (Models 1-2)
E09 | Observability, Dashboards & Delivery
E10 | Group 2 - Scale-Out (Models 3-10)
E11 | Steady State, Hypercare & Handover
E12 | Testing, UAT & Performance
E13 | Capacity & Resourcing
E14 | Model Implementation Documentation (IDG)